| ID | 012025BMP |
| --- | --- |
| OWNER | DARVYCOM AUSTRALIA PTY LTD |
| PROJECT NAME | DARVYCOM NETWORK UPGRADE AND APPLICATION DSP SYSTEMS |
| ISSUE DATE | 10/12/2025 |
| LAST DATE SAVED | 12/12/2025 |
| VERSION | 1.0 |
| APPROVAL OF SPONSOR |  |

This template provides a guide for you to complete the BUDGET MANAGEMENT PLAN

for the Darvycom Australia Pty Ltd project of cluster 6 of the ADIT TNE programme. Ensure you provide all relevant details for your final report before submission. Please refer to the project scenario of Tasks3 and 4 of Cluster 6 project for details regarding all aspects of this plan.

Table of Contents

INTRODUCTION	3

KEY COMPONENTS OF THE BUDGET MANAGEMENT PLAN	3

OBJECTIVES	3

BUDGET ALLOCATION COMPONENTS	3

CASH FLOW BREAKDOWN	4

HARDWARE AND SOFTWARE REQUIREMENTS BREAKDOWN:	6

BUDGET CONTROLS	7

BUDGET MANAGEMENT PROCESS	8

CONCLUSION	9

# INTRODUCTION

This Budget Management Plan outlines how costs will be estimated, allocated, monitored, and controlled for the Darvycom Network Upgrade and DSP Systems Project in Brisbane.

The project budget covers all expenditure required to upgrade the engineering laboratory’s telecommunications network (two blocks), implement VoIP-based services, and improve the organisation’s Digital Signal Processing (DSP) capabilities to achieve a higher signal-to-noise ratio and better service quality.

The budget is a dynamic planning and control document: it establishes an initial cost baseline and will be reviewed regularly throughout the project to reflect approved changes and updated forecasts in line with organisational project planning practices.

# KEY COMPONENTS OF THE BUDGET MANAGEMENT PLAN

Key components of this Budget Management Plan are:

- Cost categories and estimates

  - Hardware (network equipment, servers, end-user devices)

  - Software and licences (VoIP platform, operating systems, monitoring tools)

  - Labour (project management, engineering, installation, DSP analysis)

  - Training, change management, and user support

  - Travel and miscellaneous project expenses

  - Contingency reserve

- Cost baseline and allocation

  - A consolidated project cost baseline of AUD 200,000 for Stage I (network upgrade) and Stage II (DSP and engineering solutions), broken down by major category and by project month.

- Cash flow and timing of spend

  - Monthly cash flow profile reflecting when major procurement, implementation, and testing activities occur.

- Budget controls and reporting

  - Variance thresholds, approval limits, and regular status reporting to monitor budget performance against the baseline.

- Change and risk linkages

  - Integration with the Risk Management Plan and Change Management Plan so that cost impacts of risks and changes are captured and controlled.

# OBJECTIVES

The objectives of this Budget Management Plan are to:

- Maintain total project costs within the approved ceiling of AUD 200,000, including contingency and all network/DSP-related expenditure.

- Provide a clear and traceable cost baseline that links to the Work Breakdown Structure (WBS), schedule, and scope, allowing accurate tracking of costs by phase and deliverable.

- Ensure timely funding availability so that critical procurement and implementation activities are not delayed by cash-flow issues.

- Support informed decision-making by giving management regular, accurate cost information (planned vs actual vs forecast) and highlighting any variances early.

- Comply with Darvycom’s organisational policies for financial controls, approvals, and documentation for ICT project budgeting

# BUDGET ALLOCATION COMPONENTS

| Cost Category | Amount (AUD) | Notes |
| --- | --- | --- |
| Network & lab hardware | 91,800 | Physical equipment for both lab blocks and core network |
| Software & licences | 14,200 | VoIP / PBX, OS licences, monitoring & security tools |
| Labour (PM, engineers, technicians) | 68,000 | Planning, design, configuration, DSP analysis, installation |
| Training & change management | 9,000 | End-user training, technical upskilling, documentation |
| Travel & miscellaneous | 5,000 | Site visits, travel between Brisbane and Melbourne, incidentals |
| Contingency reserve (~6% of direct costs) | 12,000 | To cover unforeseen but in-scope cost variations |
| TOTAL PROJECT BUDGET | 200,000 | Budget ceiling (baseline including contingency) |

High-level allocation by stage (approximate):

- Stage I – Network Upgrade (ICTPMG613 & ICTTEN615): ~60% ≈ AUD 120,000

- Stage II – DSP & Engineering Solutions (ICTTEN826 & ICTTEN827): ~40% ≈ AUD 80,000

# CASH FLOW BREAKDOWN

Assuming a 6-month project duration, the expected cash flow is profiled to match key activities: requirements, design, procurement, installation, testing, and handover.

| Project Month | % of Total Budget | Amount (AUD) | Main Activities |
| --- | --- | --- | --- |
| Month 1 | 20% | 40,000 | Detailed planning, final design, initial deposits for hardware and software |
| Month 2 | 35% | 70,000 | Major hardware procurement (PCs, IP phones, servers, switches), initial labour for installation |
| Month 3 | 25% | 50,000 | Remaining hardware/software procurement, core network deployment, DSP platform setup |
| Month 4 | 7.5% | 15,000 | Configuration, integration between twin lab blocks, initial testing |
| Month 5 | 7.5% | 15,000 | DSP tuning, optimisation, user acceptance testing, rework |
| Month 6 | 5% | 10,000 | Final training, documentation, post-implementation review, close-out |

Total over 6 months: AUD 200,000

The cash flow will be reviewed monthly. Any significant changes (for example, major delays or supplier changes) will be raised via the Change Management Process and may require re-profiling of this schedule.

# HARDWARE AND SOFTWARE REQUIREMENTS BREAKDOWN:

### 1. Hardware Breakdown

All hardware aligns with the client’s requirement to replace the copper-based system with VoIP and upgraded network infrastructure for both twin lab blocks.

| Hardware Item | Qty | Est. Unit Cost (AUD) | Est. Total (AUD) | Notes |
| --- | --- | --- | --- | --- |
| IP phones (VoIP-capable) | 20 | 200 | 4,000 | For all engineering lab staff across both blocks |
| Desktop PCs with updated OS | 20 | 1,700 | 34,000 | For lab workstations with softphone capability |
| Headsets with microphones | 40 | 120 | 4,800 | Paired with both softphones and IP phones |
| Video conferencing system | 1 | 7,000 | 7,000 | HD camera, codec, conference phone, display integration |
| Data servers (lab/application servers) | 2 | 10,000 | 20,000 | For lab systems, data storage, and DSP workloads |
| Voice server (dedicated VoIP / PBX server) | 1 | 7,000 | 7,000 | To host Asterisk / 3CX / equivalent |
| Router with VPN capability | 1 | 3,000 | 3,000 | Secure connectivity between Brisbane and Melbourne HQ |
| Managed network switches | 4 | 1,500 | 6,000 | Core and access layer switches for both lab blocks |
| Additional infrastructure (racks, UPS upgrades, cabling, patch panels, APs, misc.) | Lump sum | – | 6,000 | To support structured cabling and network reliability |
| Total Hardware |  |  | 91,800 |  |

2. Software and Licences Breakdown

| Software / Licence Item | Est. Total (AUD) | Notes |
| --- | --- | --- |
| IP-PBX / voice platform licences (Asterisk / 3CX / equivalent) | 5,000 | Server licences, user licences, and support |
| Softphone / unified communications licences | 3,000 | For 20 PC softphone clients and integration |
| Server operating systems and CALs | 3,200 | Windows Server / Linux support and client access licences as required |
| Network monitoring and security tools | 3,000 | For performance monitoring, logging, and basic security analytics |
| Total Software & Licences | 14,200 |  |

# BUDGET CONTROLS

Budget controls will ensure that project costs remain within the approved ceiling and that any variances are identified and managed early.

Key controls:

- Cost baseline and coding

  - Establish a cost baseline of AUD 200,000 broken down by WBS element and cost category.

  - Assign cost codes to each work package (hardware, software, installation, DSP design) to track actual spend against the baseline.

- Variance thresholds

  - A variance of ±5% at the overall project level or ±10% at individual work-package level will trigger investigation and corrective actions.

  - Any change that increases total budget or moves more than AUD 5,000 between categories requires formal change approval by the project sponsor.

- Approval and authorisation

  - All purchase orders above AUD 5,000 must be approved by the Project Sponsor or delegated manager.

  - Timesheets and external invoices will be authorised by the Project Manager before payment.

- Monitoring frequency

  - Monthly budget review meetings comparing planned vs actual costs and updated forecast to complete.

  - Cost reports will be integrated with schedule status reports to ensure early detection of schedule-driven cost risk.

- Integration with risk and change management

  - Financial impacts of risks and approved changes will be reflected in the budget, using the contingency reserve where appropriate.

  - If contingency is exhausted, a formal request for additional funding must be raised and approved before committing further spend.

# BUDGET MANAGEMENT PROCESS

The following process will be used to manage the budget across the life of the project:

- Estimate and planning

  - Develop detailed cost estimates for each WBS activity (hardware, software, labour, training, DSP work) based on supplier quotes, historical data, and expert judgment.

  - Consolidate these estimates into the project budget and cost baseline, including contingency for identified risks.

- Approval

  - Present the Budget Management Plan and detailed cost breakdown to the Project Sponsor and senior management.

  - Obtain formal approval of the total budget (AUD 200,000) and of the key cost categories and cash-flow profile.

- Cost recording

  - Record all actual costs in Darvycom’s financial system and in the project cost tracking sheet (or project management software).

  - Allocate costs against the relevant WBS elements so that spend can be analysed by phase and activity.

- Monitoring and reporting

  - Prepare monthly cost performance reports showing:

    - Planned Value (PV)

    - Actual Cost (AC)

    - Estimate to Complete (ETC)

    - Variances (cost and schedule) and variance explanations.

  - Use this information to adjust forecasts and recommend corrective actions where required.

- Control and corrective actions

  - When thresholds are exceeded, the Project Manager will:

    - Identify root causes (supplier delays, scope change, under-estimated labour).

    - Propose actions such as re-prioritising work, using contingency, or adjusting scope.

    - Raise a formal Change Request if budget or scope adjustments are required.

- Review and re-baseline (if needed)

  - For major approved changes, update the cost baseline and cash-flow profile to maintain a realistic and usable budget.

  - Document changes to keep an audit trail consistent with organisational policies.

- Closure

  - At project close, prepare a final financial report summarising:

    - Original budget vs final actual spend

    - Use of contingency

    - Key cost variances and lessons learned

  - Archive budget documentation according to organisational record-keeping requirements.

# CONCLUSION

This Budget Management Plan provides a structured approach for estimating, allocating, monitoring, and controlling all costs for the Darvycom Network Upgrade and DSP Systems Project.

By clearly defining cost categories, cash flows, controls, and management processes — and by staying within the AUD 200,000 approved budget — the project team can support Darvycom’s objectives for improved network performance, better voice quality, and enhanced DSP capability, while maintaining financial discipline and complying with organisational policies.