| Student ID: | CTI20221062 |
| --- | --- |
| Student Name: | Leonardo Matias Ciarcia |

| Date/Time: | Monday, 17 November 2025, Time: 11AM |  |  |  |
| --- | --- | --- | --- | --- |
| Location: | Room 4 , Level 8, 333 Adelaide Street, Brisbane. QLD 4000 |  |  |  |
| Chairperson: | Leonardo Matias Ciarcia |  |  |  |
| Meeting Attendees: Full names and roles |  |  |  |  |
| Agenda Item/Topic | Discussion/Activities/Outcomes |  | Action Officer | Target/ Due Date |
| Welcome |  welcomed the attendees and explained that the meeting would review the project methodology, control plans, schedule and budget for the Darvycom network upgrade.  The meeting objectives and three agenda items were introduced. |  | Project Manager | 17/11/2025 |
| (Agenda item 1) Project Methodology and Control Plans Topic? - Establish how the project will be managed, monitored and controlled. | Motion moved by: Project Manager Details of discussion/activities (Points Discussed/ Activities completed); Actions Suggested.  Review the project scope, deliverables, exclusions and acceptance requirements.  Confirm the hybrid project methodology, combining structured Waterfall planning with progressive testing and review.  Review controls for scope, schedule, cost, quality, risk, communication, procurement and change requests.  Confirm that project changes must be documented, assessed and approved before implementation.;  The hybrid methodology and project control plans were accepted.  Regular status meetings and progress reports will be used to monitor performance.  Significant changes or variances will be escalated to the Project Sponsor.. Voting and Resolution:  Voting: All attendees supported the proposed methodology and control arrangements.  Resolution: The hybrid project methodology and project control plans were approved. | Project Manager | End of Project Week 2 |
| (Agenda item 2) Project Schedule Development Topic? - Establish a realistic schedule for completing the Darvycom project. | Motion moved by: Project Manager Details of discussion/activities (Points Discussed/ Activities completed); Actions Suggested.  Review the 24-week project schedule.  Confirm the stages of initiation, planning, requirements analysis, design, procurement, implementation, integration, testing, training, handover and closure.  Identify task dependencies, milestones, responsible resources and critical activities.  Discuss how delays and schedule changes will be recorded and managed.;  The Gantt chart and Project Schedule Task List were accepted as the schedule baseline.  Progress will be reviewed against planned milestones.  Delayed critical tasks will require corrective action and schedule review.. Voting and Resolution:  Voting: All attendees supported the proposed schedule.  Resolution: The 24-week Gantt chart and task list were approved as the project schedule baseline. | Project Manager and Technical Team Leaders | End of Project Week 4 |
| (Agenda item 3) Project Budget Finalisation Topic? - Approve the project budget and establish financial controls. | Motion moved by: Finance/Procurement Officer Details of discussion/activities (Points Discussed/ Activities completed); Actions Suggested.  Review labour rates, network equipment, software, installation, testing, training and cost-of-quality expenses.  Review anticipated expenditure and the timing of project cash flows.  Confirm the AUD 184,800 working cost baseline within the AUD 200,000 funding ceiling.  Review the remaining AUD 15,200 reserve and the approval process for using contingency funds.;  The working budget baseline was approved.  Purchases must follow procurement and approval procedures.  Actual spending will be compared with the budget, and cost variances will be reported.  Contingency funds cannot be used without authorisation.. Voting and Resolution:  Voting: All attendees supported the proposed budget arrangements.  Resolution: The AUD 184,800 working budget baseline was approved within the AUD 200,000 funding ceiling. | Project Manager and Finace | End of Project Week 5, before procurement begins |
| Summary | Overall Summary: The project team reviewed the management methodology, project controls, 24-week schedule and financial arrangements for the Darvycom network upgrade. Decision/s:  The hybrid project methodology was approved.  The project control plans were accepted.  The 24-week schedule was approved as the schedule baseline.  The AUD 184,800 working budget was approved within the AUD 200,000 ceiling. Action/s if any:  The Project Manager will distribute the approved plans.  Technical Team Leaders will monitor assigned activities.  The Finance/Procurement Officer will monitor expenditure and procurement.  Project progress, costs, risks and changes will be reviewed regularly. |  |  |  |
| Next Meeting time/date | 19/01/2026 |  | Leonardo | 17/11/2025 |
| Meeting closed at: | 12PM |  | Leonardo | 17/11/2025 |
| Minutes are a true and accurate record of the meeting | Approved/confirmed by: (who?) Dijo Sasidharan |  | Dijo Sasidharan | 17/11/2025 |
| Signature of attendee 1: Leonardo |  | Signature of attendee 3: Dijo |  |  |