## Gantt Chart
Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade – Gantt Chart (Initial Version)
Task ID | Task name | Start week | End week | Duration (weeks) | Main dependency | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24
1 | Initiation and project charter | 1 | 2 | 2 | – | bar: Week 1 to Week 2
2 | Project Management Plan and subplans | 2 | 4 | 3 | Task 1 | bar: Week 2 to Week 4
3 | Stakeholder setup and kick-off meeting | 3 | 4 | 2 | Task 1, Task 2 | bar: Week 3 to Week 4
4 | Requirements gathering and site analysis | 5 | 6 | 2 | Task 3 | bar: Week 5 to Week 6
5 | Project specifications and attributes | 6 | 7 | 2 | Task 4 | bar: Week 6 to Week 7
6 | Network architecture and logical design | 7 | 8 | 2 | Task 5 | bar: Week 7 to Week 8
7 | VoIP and collaboration design | 8 | 9 | 2 | Task 6 | bar: Week 8 to Week 9
8 | DSP design and analysis | 9 | 10 | 2 | Task 5 | bar: Week 9 to Week 10
9 | Consolidated design documentation and sign-off | 10 | 11 | 2 | Tasks 6, 7, 8 | bar: Week 10 to Week 11
10 | Procurement and supplier selection | 12 | 13 | 2 | Task 9 | bar: Week 12 to Week 13
11 | Delivery, verification and lab preparation | 14 | 15 | 2 | Task 10 | bar: Week 14 to Week 15
12 | Network implementation (switches, router, servers) | 16 | 17 | 2 | Task 11 | bar: Week 16 to Week 17
13 | VoIP, video and DSP implementation | 18 | 19 | 2 | Task 12 | bar: Week 18 to Week 19
14 | Testing (network, VoIP, DSP) and UAT | 20 | 22 | 3 | Task 13 | bar: Week 20 to Week 22
15 | Training, handover and project closure | 23 | 24 | 2 | Task 14 | bar: Week 23 to Week 24