# PROJECT DETAILS SUMMARY

Project: Darvycom Brisbane Engineering Laboratory Network & DSP Upgrade
Project Manager:  Leonardo Matias Ciarcia
Date: 20/11/2025

## 1. Company’s Specifications and Project Background

| Project detail | Information |
| --- | --- |
| Name of the company | Darvycom Australia Pty Ltd |
| Headquarters location | Not specified in the current project documents |
| Project implementation location | Darvycom Brisbane Engineering Laboratory, covering two laboratory blocks |
| Services provided to customers | Darvycom provides telecommunications engineering, network communication and digital signal-processing services. Its activities include the analysis of analogue and digital signals, signal conversion using ADC and DAC processes, voice communication, network services, technical testing and engineering support for commercial and research and development activities. |
| Company’s objectives and necessities | Darvycom needs to improve the reliability, capacity, security and quality of its Brisbane laboratory communication systems. The existing copper-based voice system and limited data network do not adequately support modern VoIP, video conferencing, secure remote connectivity, engineering applications or DSP analysis. |
| Project goal | Upgrade the Brisbane Engineering Laboratory into a reliable regional office environment by implementing a secure IP-based network, VoIP, video conferencing, server services, monitoring and an improved DSP configuration. |
| How the company will improve | Replace the analogue telephone and hybrid PBX environment with VoIP and an IP-PBX; upgrade the network using managed PoE switches and Layer 3 services; introduce VLANs, QoS, VPN and access controls; deploy new servers, computers, phones and video conferencing; implement PRTG monitoring; and integrate a tested DSP solution that improves signal quality and reduces noise. |
| Users’ complaints and identified problems | Poor voice quality; limited telephone features; old computer operating systems; insufficient switch ports; little or no PoE support; limited QoS; no VPN capability; one data server creating a single point of failure; no dedicated video-conferencing system; no headsets; and no dedicated DSP simulation and analysis environment. |
| Existing infrastructure at the Brisbane laboratory | 8 analogue telephones connected through copper cabling; 8 desktop computers; 1 data server; 1 Panasonic Hybrid PBX; 1 basic Internet router without VPN capability; 2 basic network switches with limited management, PoE and QoS functions; and 1 UPS supporting the existing limited load. |
| Existing network characteristics | The current network is mainly wire-based and uses copper connections. It has limited scalability, minimal traffic separation, limited monitoring and insufficient support for real-time voice, video and DSP traffic. |
| Expected operational outcome | A secure, scalable and monitored network that allows both laboratory blocks to communicate and supports high-quality voice, video conferencing, data services, wireless connectivity, DSP applications and future organisational growth. |

## 2. Project Details and Document Control

| Project detail | Information |
| --- | --- |
| Project name | Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade |
| Project type | Network Upgrade and DSP Improvement Project |
| Reference documents | Project Management Plan (PMP); Existing vs Expected specification; Darvycom Initial Gantt Chart; approved network topology; IP schema; Packet Tracer configurations; DSP design and simulation reports; network traffic analysis reports |
| Document ID | DARV-C6-PDS-001 |
| Document owner | Darvycom Australia Pty Ltd |
| Prepared by | Leonardo Matias Ciarcia |
| Issue date | 19/12/2025 |
| File name | Project_Details_Summary_Darvycom_v1.0 |
| Document history | Initial Project Details Summary developed from the approved project planning, network, traffic-management, DSP and engineering solution documents |
| Version | 1.0 |
| Document approvals | Darvycom Project Sponsor/Client Representative and Leonardo Matias Ciarcia, Project Manager |
| Project kickoff | Week 1 of the approved project schedule |
| Initial project budget | AUD 184,800 |
| Project duration | Approximately six months or 24 project weeks |
| Project methodology | Hybrid methodology. A predictive approach is used for planning, procurement, infrastructure implementation, testing and handover. An iterative approach is used for DSP modelling, simulation, comparison, parameter adjustment and validation. |
| Procurement approach | Equipment and licences will be purchased following Darvycom’s procurement and approval procedures. Suppliers will be evaluated according to compatibility, price, delivery time, support and compliance. |
| Monitoring approach | Progress will be monitored against the 24-week Gantt chart, project budget, risk register, test results and acceptance criteria. PRTG will monitor network availability, utilisation, latency, packet loss, interfaces and essential services. |
| Strategy to improve the network | Upgrade the Brisbane laboratory so it can operate as a regional office, replace the legacy voice environment, connect both laboratory blocks, introduce secure network segmentation and monitoring, and provide sufficient capacity for voice, data, video and DSP workloads. |

### Project phases

| Stage and phase | Activities |
| --- | --- |
| Stage I – Phase 1: Project planning and network upgrade | Confirm requirements, assess existing infrastructure, develop the project plans, prepare network designs, evaluate solution options, select the final solution and obtain approval. |
| Stage I – Phase 2: Network traffic management | Analyse existing and expected traffic, establish performance thresholds, identify congestion risks, implement QoS and traffic controls, configure PRTG monitoring and prepare capacity recommendations. |
| Stage II – Phase 3: DSP analysis and evaluation | Analyse communication signals, investigate time-domain and frequency-domain behaviour, evaluate filtering methods, conduct convolution and Fourier analysis, and compare analytical and simulated results. |
| Stage II – Phase 4: Engineering solution and validation | Develop and simulate the final engineering solution, implement the selected DSP configuration, integrate it with the communication environment, conduct testing and document the final outcomes. |

### Implementation phases

| Implementation phase | Timing |
| --- | --- |
| Initiation and planning | Weeks 1–4 |
| Requirements and site analysis | Weeks 5–7 |
| Network, voice and DSP design | Weeks 7–11 |
| Procurement and laboratory preparation | Weeks 12–15 |
| Network implementation | Weeks 16–17 |
| VoIP, video and DSP integration | Weeks 18–19 |
| Technical testing and user acceptance | Weeks 20–22 |
| Training, handover and closure | Weeks 23–24 |

## 3. Project Aspects, Governance and Resources

| Project detail | Information |
| --- | --- |
| Project established by | Darvycom Australia Pty Ltd authorised Project Sponsor/Client Representative |
| Project sponsor | Darvycom Australia Pty Ltd authorised representative |
| Client/IT representative | Darvycom IT and Operations representative |
| Contact for project support | Leonardo Matias Ciarcia, Project Manager, together with the assigned network, systems, voice and DSP technical specialists |
| Project Manager | Leonardo Matias Ciarcia |
| Project Manager duties | Oversee the complete network upgrade and DSP improvement project; manage scope, schedule, budget, quality, risk, communication, procurement and changes; coordinate the project team; review technical progress; manage rollout and testing; ensure the required resources are available; and obtain final acceptance and project closure. |
| Project team members | Project Sponsor/Client Representative; Leonardo Matias Ciarcia – Project Manager and Technical Specialist; Network Engineer; Voice and Collaboration Engineer; DSP Engineer; Systems Administrator; Network Traffic Analyst; Procurement Representative; Finance Representative; Test and UAT Coordinator; Laboratory User Representatives; and equipment suppliers or vendor-support personnel. |
| Project methodology | Hybrid project methodology using predictive infrastructure delivery and iterative DSP development and testing |
| Project communication plan | Weekly project status meetings; regular progress, budget and risk reports; design-review and approval meetings; email communication and controlled project documents; daily coordination during implementation and cutover; immediate escalation of critical issues; implementation notices to affected staff; training sessions; and final handover meetings. |
| Change-control process | Proposed changes will be assessed for their effects on scope, cost, schedule, risk, quality and resources. Significant changes require documented approval before implementation. |
| Quality-management approach | Use approved design standards, configuration reviews, staged implementation, technical testing, PRTG performance data, DSP measurements, user acceptance testing, defect correction and final sign-off. |
| Rollout strategy | Preconfigure and test equipment before deployment; implement one laboratory block as a pilot; review technical tests and user feedback; deploy the validated configuration to the second block; provide stabilisation support; and complete training and handover. |
| Risk-management approach | Maintain a risk register covering requirements, procurement, compatibility, PoE and UPS capacity, security, network congestion, voice quality, DSP performance, operational disruption, budget and schedule risks. |
| Project acceptance | Acceptance requires successful network, voice, video, security, monitoring, DSP and UAT results; no unresolved critical or high-severity defects; delivery of documentation and training; and signed client approval. |

## 4. Future Network Infrastructure to Deploy

| Resource category | Future infrastructure |
| --- | --- |
| Network architecture | Internet/ISP connection, VPN-capable edge router, firewall/access-control function, Layer 3 core services and managed access/distribution infrastructure connecting both laboratory blocks |
| Computers | 20 desktop computers with updated operating systems, engineering applications and softphone capability |
| Voice equipment | 20 IP phones using VoIP |
| Headsets | 40 headsets with microphones |
| Video collaboration | 1 video-conferencing system |
| Data servers | 2 data servers supporting applications, storage, laboratory services and backup requirements |
| Voice server | 1 voice server providing central IP-PBX functionality |
| Router | 1 router with VPN capability |
| Network switches | 4 managed PoE switches supporting VLANs, QoS, trunking and endpoint power |
| Wireless infrastructure | Wireless access points and associated control functions for approved wireless connectivity across the laboratory blocks |
| Network segmentation | Separate voice, data, wireless, server and management VLANs using the approved IP-addressing schema |
| Routing and traffic control | Inter-VLAN routing, access controls and QoS prioritisation for VoIP, video conferencing and other real-time applications |
| Security | VPN, firewalling, ACLs, protected administration, endpoint security, patching, logging and least-privilege access |
| Monitoring | PRTG monitoring for device availability, interfaces, bandwidth, utilisation, latency, packet loss, servers and essential services |
| DSP resources | DSP simulation and analysis software supporting time-domain and frequency-domain analysis, Fourier/FFT operations, filtering, convolution, SNR measurement and comparison of analytical and simulated results |
| Power protection | Existing UPS with a capacity review and upgrade where required to support switches, routers and servers |
| Backup and recovery | Server backups, network-device configuration backups, DSP configuration records and tested restoration procedures |
| Documentation | Updated topology, IP schema, device and port records, configuration backups, test reports, user guides and technical handover documents |