# PROJECT IMPLEMENTATION PLAN

Project: Darvycom Brisbane Engineering Laboratory Network & DSP Upgrade
Project Manager:  Leonardo Matias Ciarcia
Date: 05/02/2026

## 1. Project Overview

Darvycom Australia is upgrading its Brisbane Engineering Laboratory so it can operate effectively as a regional office supporting commercial and research and development activities. The existing environment uses copper-based analogue telephony, a legacy Panasonic Hybrid PBX and a limited data network. This has resulted in poor voice quality, limited capacity, insufficient collaboration facilities and reduced support for modern engineering and Digital Signal Processing (DSP) activities.

The project will implement an integrated IP-based network and communication solution across the two laboratory blocks. The final environment will support VoIP, video conferencing, secure data services, DSP applications, remote connectivity and centralised network monitoring.

The solution will include:

- 20 IP phones using VoIP

- 20 computers with updated operating systems and softphone capability

- 40 headsets with microphones

- One video-conferencing system

- Two data servers

- One voice server providing IP-PBX functionality

- One VPN-capable router

- Four managed PoE network switches

- Voice, data, wireless, server and management VLANs

- QoS for VoIP and other real-time traffic

- Firewalling, access control, VPN and endpoint security

- PRTG network monitoring

- An integrated and tuned DSP configuration

- Updated UPS, backup and recovery arrangements where required

The logical architecture will connect the Internet/ISP service to the VPN edge and firewall, followed by the Layer 3 core and managed access/distribution switches servicing both laboratory blocks. The data servers, voice server, monitoring services, video-conferencing system, IP phones and computers will connect through the approved VLAN and IP-addressing design.

The infrastructure implementation will use a predictive project lifecycle, while the DSP activities will follow an iterative design, simulation, testing and refinement process.

### Project objectives

The objectives are to:

- Replace the existing copper-based telephony system with a reliable IP-based voice solution.

- Improve voice quality and reduce unwanted noise and interference.

- Upgrade both laboratory blocks to support current and future voice, data, video and DSP requirements.

- Provide secure connectivity through VPN, firewalling and controlled access.

- Separate network traffic through VLANs and prioritise voice and video through QoS.

- Implement PRTG monitoring for network availability, utilisation, performance and alerts.

- Provide documentation and training so Darvycom staff can operate and support the environment.

- Complete the project within the approved 24-week schedule and AUD 184,800 baseline budget.

## 2. Scope

### 2.1 In scope

The project includes:

- Reviewing the existing network, telephony, server, power and DSP environment.

- Conducting an assessment of both Brisbane laboratory blocks.

- Developing the physical and logical network design.

- Developing the approved IP-addressing and VLAN schema.

- Configuring routing, VLANs, trunk links, QoS, VPN and access controls.

- Procuring and implementing one VPN-capable router.

- Procuring and implementing four managed PoE switches.

- Installing and configuring two data servers.

- Installing and configuring one voice server with IP-PBX functionality.

- Deploying 20 IP phones and 40 headsets.

- Preparing 20 computers with updated operating systems and softphones.

- Installing and configuring one video-conferencing system.

- Configuring PRTG sensors, thresholds, alerts and performance reports.

- Reviewing UPS capacity and providing sufficient protection for core devices.

- Configuring backups for servers and network-device configurations.

- Analysing, modelling, simulating and implementing the DSP solution.

- Comparing analytical and simulated DSP results.

- Measuring signal quality, noise reduction and DSP stability.

- Conducting network, voice, video, security, DSP and user acceptance testing.

- Correcting identified defects and completing retesting.

- Providing user guides, technical documentation and configuration records.

- Delivering training and handing the solution over to Darvycom operations.

- Completing the project closure report and lessons learned.

### 2.2 Out of scope

The following activities are outside the project scope:

- Major network or telephony changes at Darvycom locations other than the Brisbane Engineering Laboratory.

- Replacement of more than the 20 approved end-user computers.

- Organisation-wide application or business-process redesign.

- Unapproved building or electrical works.

- New carrier services that are not required for the approved solution.

- Additional network devices or user capacity not included in the approved requirements.

- Ongoing operational support after the agreed stabilisation and handover period.

### 2.3 Scope control

Detailed IP addresses, VLAN assignments, interfaces, dial-plan values and DSP parameters will be maintained in the approved design and configuration records. Any change affecting the approved scope, budget, completion date, equipment quantities or acceptance criteria must be evaluated and approved through the formal project change-control process.

3. Deliverables

| ID | Deliverable | Description and completion evidence |
| --- | --- | --- |
| D1 | Approved project documentation | Project Management Plan, implementation plan and required management subplans approved and controlled. |
| D2 | Requirements and current-state assessment | Site assessment, existing-versus-expected specification and confirmed network, voice and DSP requirements. |
| D3 | Network architecture and logical design | Approved topology, IP schema, VLANs, routing, QoS, VPN, security, voice and video-conferencing design. |
| D4 | DSP design package | Analytical models, simulations, candidate configurations, selected parameters and DSP design report. |
| D5 | Procured and verified equipment | Router, switches, servers, phones, headsets, computers, video system and licences received and recorded. |
| D6 | Implemented network infrastructure | VPN edge, Layer 3 services, managed switching, VLANs, routing, QoS, security and connectivity across both blocks. |
| D7 | Voice and collaboration services | Operational IP-PBX, dial plan, IP phones, softphones, headsets and video-conferencing system. |
| D8 | Server and monitoring services | Two data servers, backup arrangements, protected administration and operational PRTG monitoring. |
| D9 | Integrated DSP solution | Selected and tuned DSP configuration integrated into the communication environment. |
| D10 | Testing and acceptance package | Network, voice, video, VPN, security, performance, DSP and UAT results, including defect and retest records. |
| D11 | Training and handover package | User guides, technical documentation, configuration records, training evidence and handover checklist. |
| D12 | Project closure report | Final project status, expenditure, lessons learned, outstanding actions and closure approval. |

4. Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project sponsor/client representative | Approves the scope, budget, major changes, consolidated design, final acceptance and project closure. |
| Project Manager – Leonardo Matias Ciarcia | Manages the schedule, budget, scope, risks, communications, procurement coordination, change control, reporting, implementation, rollout and handover. |
| Network engineer | Configures the VPN router, firewall/access controls, Layer 3 services, VLANs, routing, QoS, managed PoE switches and PRTG network sensors. Maintains configuration backups. |
| Voice and collaboration engineer | Configures the voice server, IP-PBX, dial plan, phones, softphones, headsets, SIP security and video-conferencing system. Conducts voice and video testing. |
| DSP engineer | Establishes DSP objectives, models and simulates candidate filters, compares analytical and simulated results, tunes the selected configuration and tests SNR and stability. |
| Systems administrator | Installs and secures the data and voice servers, manages accounts, updates, endpoint protection, backups and recovery testing. |
| Procurement representative | Obtains quotations, evaluates suppliers, issues approved purchase orders, tracks delivery and verifies equipment and licences. |
| Finance representative | Monitors commitments and actual costs against the AUD 184,800 baseline and reports budget variances. |
| Test and UAT coordinator | Prepares test plans, manages test evidence and defects, coordinates retesting and recommends technical acceptance. |
| Laboratory operations representatives | Confirm operational requirements, support implementation windows, participate in UAT, attend training and receive the handover. |
| Equipment suppliers/vendors | Deliver equipment and licences and provide product documentation, warranty and technical escalation support. |

## 5. Implementation Schedule (Gantt)

The project will be delivered over 24 weeks. The critical path progresses from initiation and planning to requirements, design approval, procurement, implementation, testing, acceptance, training and closure.

| Task ID | Task | Start week | End week | Duration | Dependency |
| --- | --- | --- | --- | --- | --- |
| 1 | Initiation and project charter | 1 | 2 | 2 weeks | None |
| 2 | Project Management Plan and subplans | 2 | 4 | 3 weeks | Task 1 |
| 3 | Stakeholder setup and kick-off meeting | 3 | 4 | 2 weeks | Tasks 1 and 2 |
| 4 | Requirements gathering and site analysis | 5 | 6 | 2 weeks | Task 3 |
| 5 | Project specifications and attributes | 6 | 7 | 2 weeks | Task 4 |
| 6 | Network architecture and logical design | 7 | 8 | 2 weeks | Task 5 |
| 7 | VoIP and collaboration design | 8 | 9 | 2 weeks | Task 6 |
| 8 | DSP design and analysis | 9 | 10 | 2 weeks | Task 5 |
| 9 | Consolidated design documentation and sign-off | 10 | 11 | 2 weeks | Tasks 6, 7 and 8 |
| 10 | Procurement and supplier selection | 12 | 13 | 2 weeks | Task 9 |
| 11 | Delivery, verification and laboratory preparation | 14 | 15 | 2 weeks | Task 10 |
| 12 | Network implementation – switches, router and servers | 16 | 17 | 2 weeks | Task 11 |
| 13 | VoIP, video and DSP implementation | 18 | 19 | 2 weeks | Task 12 |
| 14 | Network, VoIP and DSP testing and UAT | 20 | 22 | 3 weeks | Task 13 |
| 15 | Training, handover and project closure | 23 | 24 | 2 weeks | Task 14 |

Progress will be reviewed weekly against the task dependencies and critical path. Documentation and training preparation may run in parallel where this does not interfere with design approval, procurement or testing. Forecast delays will be assessed for corrective action before a schedule change is requested.

6. Risks & Mitigations

| ID | Risk | Likelihood | Impact |  | Mitigation and contingency |
| --- | --- | --- | --- | --- | --- |
| R1 | Incomplete or changing requirements | Medium | High | Confirm requirements early, document them clearly and obtain design sign-off. Process later changes through formal change control. |  |
| R2 | Late delivery of equipment or licences | Medium | High | Order critical equipment early, monitor supplier dates and identify compatible alternatives. Resequence preparation work where possible. |  |
| R3 | Insufficient ports, PoE capacity, cabling or UPS capacity | Medium | High | Validate port counts, PoE power, cabling, rack space and UPS load before procurement. Use approved contingency funds to add capacity if required. |  |
| R4 | Configuration error causes an outage | Medium | High | Stage and peer-review configurations and back up existing devices before changes. Restore the last known-good configuration if required. |  |
| R5 | Congestion affects voice and video quality | Medium | High | Separate traffic with VLANs, apply QoS, monitor utilisation through PRTG and test under representative loads. Increase or redistribute capacity if necessary. |  |
| R6 | VPN, firewall or access-control weakness | Low | High | Apply least privilege, strong authentication, patching, ACL review and negative security testing. Disable affected access and restore approved security settings if a failure occurs. |  |
| R7 | IP-PBX, phone or video incompatibility | Medium | High | Confirm standards, firmware and licensing during design and staging. Escalate to the supplier or use an approved compatible replacement. |  |
| R8 | DSP configuration does not improve signal quality | Medium | High | Compare analytical and simulation results and test candidate filter parameters before integration. Return to the last stable DSP configuration if performance is reduced. |  |
| R9 | Cutover disrupts laboratory operations | Medium | High | Use agreed maintenance windows, a Block A pilot, advance communication and rollback procedures. Return the affected block to the legacy environment if necessary. |  |
| R10 | Users are not ready to operate the system | Medium | Medium | Provide guides, demonstrations, training and supervised UAT. Extend the stabilisation period and provide refresher training if required. |  |
| R11 | Project exceeds budget or schedule | Medium | High | Track costs, commitments, critical-path progress and contingency use. Apply corrective action or submit an approved change request. |  |
| R12 | Loss of server or configuration data | Low | High | Complete and verify backups before implementation. Test restoration and retain protected configuration copies. |  |

The Project Manager will maintain the risk register and review risks during project status meetings. Critical risks or issues affecting security, data integrity, voice availability, budget or the completion date will be escalated immediately.

## 7. Testing Procedures

Testing will first be performed in Cisco Packet Tracer and the DSP simulation environment. The approved configurations will then be tested during staging, implementation and user acceptance.

Each test record must contain:

- Test identification number

- Date and tester

- Configuration version

- Test steps and input

- Expected result

- Actual result

- Evidence or screenshot reference

- Pass or fail status

- Defect reference where applicable

### 7.1 Test readiness

Before testing begins:

- Confirm that the network design, IP schema, dial plan and DSP parameters have been approved.

- Verify that all required equipment, firmware and licences are available.

- Confirm cabling, power, PoE and UPS readiness.

- Back up the existing router, switches, PBX, servers and relevant configuration records.

- Confirm that PRTG sensors and logging are operating.

- Confirm that the testing window has been communicated to laboratory staff.

- Obtain test-entry approval from the Project Manager.

### 7.2 Technical testing

| Test | Area | Procedure | Expected result |
| --- | --- | --- | --- |
| T01 | Physical and device readiness | Inspect cabling, interfaces, link lights, PoE delivery, power, UPS, firmware and device inventory. | All required devices operate on the approved interfaces without unresolved hardware faults. |
| T02 | VLANs and addressing | Verify access and trunk ports, VLAN membership, DHCP or static addresses, subnet masks, gateways and name resolution. | Endpoints use the correct addressing and remain separated according to the design. |
| T03 | Connectivity and routing | Use ping, traceroute and Packet Tracer Simulation Mode to test same-VLAN, inter-VLAN, inter-block, server, gateway and Internet paths. | All approved paths succeed through the expected route. Prohibited paths fail. |
| T04 | VPN and access control | Establish authorised VPN access and test required resources. Attempt access with invalid credentials and from prohibited networks. | Authorised VPN access succeeds. Unauthorised access is blocked and logged. |
| T05 | Data servers and backups | Test approved server services, permissions and backup completion. Restore a controlled sample. | Services are available to authorised users and the restored data is complete and usable. |
| T06 | IP-PBX and voice | Confirm registration of phones and softphones. Test calls within and between blocks, transfer, hold and approved external calls. | All approved extensions register and complete the required call scenarios with clear and stable audio. |
| T07 | Video conferencing | Start a test meeting and verify camera, microphone, speaker, content sharing and operation during concurrent network use. | The meeting connects and remains usable without material interruption. |
| T08 | QoS and network load | Generate representative voice, video, DSP and data traffic. Review queue counters and PRTG performance information. | Voice and video remain prioritised and network performance stays within approved thresholds. |
| T09 | PRTG monitoring | Verify availability, interface, utilisation, latency, packet-loss and service sensors. Trigger test alerts. | Sensors collect data and alerts are created, acknowledged and cleared correctly. |
| T10 | Security and recovery | Review patching, endpoint protection, management access and least privilege. Test configuration restoration and rollback. | Security controls operate as designed and services can be recovered successfully. |
| T11 | DSP performance | Apply controlled signals and noise. Compare input/output waveforms, frequency responses, SNR, stability and analytical/simulated results. | The selected DSP configuration provides measurable signal-quality improvement without unacceptable distortion or instability. |
| T12 | User acceptance testing | Users perform normal calling, video, server-access and DSP-related activities using approved UAT scripts. | All critical UAT cases pass and users confirm the solution meets operational requirements. |

Voice-performance targets during representative testing should include:

- One-way latency below 150 milliseconds

- Jitter below 30 milliseconds

- Packet loss below 1%

- Clear and intelligible audio without material echo or repeated dropouts

### 7.3 Defect and retesting procedure

- Record every failed test in the defect register.

- Assign a severity, owner and required resolution date.

- Stop the affected rollout where the defect threatens security, data integrity or essential service availability.

- Correct the hardware, software, configuration or DSP parameter under configuration control.

- Repeat the failed test.

- Conduct regression testing on related services.

- Close the defect only after the Test and UAT Coordinator verifies the evidence.

- Document any accepted minor limitation, workaround, responsible person and planned resolution date.

## 8. Rollout Plan

The rollout will use a staged block-by-block approach. The existing network and PBX will remain available for rollback until the pilot has passed its technical and user acceptance gates.

| Stage | Timing | Activities |
| --- | --- | --- |
| 1. Readiness and change freeze | Weeks 14–15 | Verify equipment, licences, rack space, cabling, UPS, approved designs, backups, test scripts, implementation notices and rollback materials. Prevent unapproved configuration changes. |
| 2. Offline staging | Weeks 15–16 | Preconfigure the router, switches, servers, IP-PBX, phones, PRTG monitoring and DSP parameters. Conduct bench testing and peer review. |
| 3. Block A pilot | Weeks 16–20 | Install the network foundation and migrate selected endpoints in the first laboratory block. Validate network, voice, video, monitoring and DSP services. |
| 4. Pilot decision gate | Week 20 | Review technical results, defects, PRTG information and user feedback. Continue only if critical pilot criteria have passed. |
| 5. Block B rollout | Weeks 20–22 | Apply the validated configuration to the second block. Test inter-block connectivity and repeat required technical and user tests. |
| 6. Stabilisation and hypercare | Weeks 22–23 | Monitor availability and performance closely, correct residual issues, verify backups and update the as-built documentation. |
| 7. Training and handover | Weeks 23–24 | Deliver staff training, transfer documentation and configuration records, obtain acceptance and complete project closure. |

### 8.1 Cutover controls

The implementation team will:

- Take timestamped backups before every cutover.

- Use an approved implementation checklist.

- Record each device, interface, configuration version, person and completion time.

- Maintain the legacy service until the relevant rollout gate has passed.

- Provide a single escalation contact during cutover.

- Communicate status at agreed checkpoints.

- Stop the rollout if a critical defect remains unresolved.

### 8.2 Rollback triggers

Rollback will be initiated if:

- Core connectivity, voice or essential server access cannot be restored within the agreed cutover window.

- A significant security weakness or unauthorised access path is identified.

- Data corruption or a failed server recovery occurs.

- Voice or video quality remains unacceptable after QoS correction.

- The DSP implementation becomes unstable or reduces signal quality.

- A critical test fails and cannot be corrected safely during the maintenance window.

### 8.3 Rollback actions

The team will:

- Stop the affected rollout.

- Isolate the affected equipment or service.

- Restore the last known-good router, switch, server, IP-PBX or DSP configuration.

- Reconnect the affected block to the legacy PBX or network service where required.

- Verify essential services.

- Notify stakeholders of the rollback status.

- Record the cause, actions and evidence.

- Correct and retest the solution in staging before scheduling another cutover.

## 9. Acceptance Criteria

| ID | Acceptance criterion | Required evidence |
| --- | --- | --- |
| AC01 | One VPN-capable router, four managed PoE switches, two data servers, one voice server, 20 IP phones, 40 headsets, 20 updated computers and one video-conferencing system are installed and operational. | Asset register, installation checklist and device-status evidence |
| AC02 | The approved VLAN, addressing, trunking, routing and access-control design operates across both laboratory blocks. | Configuration records and VLAN/connectivity test results |
| AC03 | All authorised endpoints can access their approved gateways, servers, inter-block services and Internet/VPN destinations. | Connectivity matrix, ping, traceroute and simulation evidence |
| AC04 | Prohibited or unauthorised network paths are blocked and logged. | ACL, firewall and negative security-test evidence |
| AC05 | All IP phones and approved softphones register successfully with the IP-PBX. | Registration and voice-server evidence |
| AC06 | Required internal, inter-block and approved external call scenarios complete successfully with stable and intelligible audio. | Call test report |
| AC07 | The video-conferencing system successfully completes the required meeting scenarios during representative network traffic. | Video-conferencing test checklist |
| AC08 | QoS prioritises voice and video traffic and performance remains within the approved latency, jitter and packet-loss targets. | QoS counters and PRTG performance report |
| AC09 | PRTG monitors all agreed core devices, interfaces and services, and test alerts operate correctly. | PRTG sensor, alert and report evidence |
| AC10 | VPN, access control, patching, protected administration, backup, recovery and rollback tests pass. | Security and recovery test report |
| AC11 | The selected DSP configuration produces a measurable improvement against the recorded signal-quality baseline and remains stable. | DSP waveforms, frequency analysis, SNR comparison and signed result |
| AC12 | All critical network, voice, video, DSP and UAT cases pass. | Approved test report and signed UAT record |
| AC13 | No unresolved critical or high-severity defect remains. | Final defect register |
| AC14 | Any accepted minor defect has a documented workaround, owner and resolution date. | Approved exception or outstanding-action register |
| AC15 | As-built diagrams, IP schema, configuration records, user guides, technical guides, backups, licences and asset records are handed over. | Signed handover checklist |
| AC16 | Nominated staff complete the required user and technical training. | Training materials and attendance records |
| AC17 | Final expenditure remains within the approved baseline or an authorised change. | Final budget report |
| AC18 | The sponsor or client representative signs the final acceptance and project closure records. | Signed acceptance and closure forms |

Final acceptance will be granted when the approved scope has been delivered, mandatory technical and user tests have passed, no critical or high-severity defect remains, documentation and training have been completed, and the client representative has signed the acceptance record.

If a mandatory criterion is not met, the affected deliverable will remain conditionally rejected until corrective action and retesting are completed, unless the sponsor or client representative formally accepts a documented exception.