Project Budge & Cash Flow Document

Project: Darvycom Brisbane Engineering Laboratory Network & DSP Upgrade
Prepared by: Leonardo Matias Ciarcia
Date: 18/12/2025

- Introduction

This document presents the consolidated budget and cash flow for the Darvycom Brisbane Engineering Laboratory network and digital signal processing (DSP) upgrade.
It summarises the total cost of the solution, shows how the budget is distributed across cost categories, and outlines when the project funds are expected to be spent over the project timeline.

The figures are aligned with the scope, design approach and cost structure already defined in the project and cost management plans.

- Budget assumptions

The budget is based on the following assumptions:

- The project covers both laboratory blocks in Brisbane, including network upgrade, VoIP, video conferencing and DSP improvements.

- The solution includes:

  - 20 IP phones

  - 20 computers with updated operating systems and softphone capability (client-funded or already planned)

  - 40 headsets with microphone

  - 1 video conferencing system

  - 2 data servers

  - 1 voice server

  - 1 router with VPN capability

  - 4 managed switches

- The preferred design is a dual-block distributed network with shared core services and local (on-premise) DSP.

- All costs are in Australian dollars (AUD).

- Costs include hardware, software, implementation, project management, documentation, training and contingency.

- Budget summary

The table below shows the budget grouped by major cost category.

| Budget category | Amount (AUD) |
| --- | --- |
| Network hardware (switches, router, phones, headsets, video conferencing) | 40,000 |
| Servers and voice platform | 34,000 |
| Software and licences (OS, voice platform, monitoring, DSP tools) | 20,000 |
| Infrastructure, racks and UPS | 12,000 |
| Implementation and configuration services | 25,000 |
| Project management, documentation and training | 23,000 |
| Contingency (approximately 20% of direct costs) | 30,800 |
| Total project budget | 184,800 |

Direct costs (before contingency) total 154,000 AUD.
A contingency of 30,800 AUD has been added to cover uncertainties in pricing, minor scope refinements and implementation risks. The total planned budget remains within the overall limit discussed with the sponsor.

- Detailed budget breakdown

Network hardware – 40,000 AUD (approximate)

- Four managed PoE switches for both blocks

- One business-grade router with VPN capability

- Twenty IP phones

- Forty headsets with microphone

- One room-based video conferencing system

Servers and voice platform – 34,000 AUD (approximate)

- Two rack-mounted data servers (including basic storage capacity)

- One dedicated voice server for IP-PBX functionality

Software and licences – 20,000 AUD (approximate)

- Operating systems and server licences

- Voice platform software and call features

- Monitoring and management tools

- DSP-related software licences and tools required for design and deployment

Infrastructure, racks and UPS – 12,000 AUD (approximate)

- Network racks, patch panels and structured cabling

- Power distribution and UPS adjustments for the new equipment

Implementation and configuration services – 25,000 AUD (approximate)

- Network configuration (switches, router, VLANs, QoS, VPN)

- VoIP, video and voice server configuration

- DSP implementation and tuning in the live environment

- Support during cutover and stabilisation

Project management, documentation and training – 23,000 AUD (approximate)

- Planning, scheduling and coordination

- Preparation of design documents, subplans, test plans and reports

- Training material and user guides

- Training sessions for laboratory staff

Contingency – 30,800 AUD

- Held centrally and released only through the agreed change and cost control processes.

- Cash flow overview

The project is planned over approximately six months.
The table below shows the expected cash flow by project month. Amounts are indicative and help to understand when funds are likely to be committed and paid.

| Project month | Main activities and commitments | Estimated spend (AUD) |
| --- | --- | --- |
| Month 1 | Initiation, planning, PMP and subplans, initial stakeholder work | 10,000 |
| Month 2 | Requirements analysis, site assessment, high-level design work (network and DSP) | 18,000 |
| Month 3 | Finalisation of designs, bill of materials and procurement preparation | 20,000 |
| Month 4 | Placement of purchase orders, main hardware and software purchases | 80,000 |
| Month 5 | Implementation labour (network, voice, DSP), infrastructure installation | 36,000 |
| Month 6 | Testing, user acceptance, documentation, training, project closure and remaining contingency | 20,800 |
| Total |  | 184,800 |

Explanation:

- Month 1–3

  - Main costs are internal labour for project management, analysis and design.

  - Limited external spend until designs and bill of materials are finalised.

- Month 4

  - The largest part of the budget is used when hardware and software orders are placed.

  - This includes network devices, servers, licences, video conferencing equipment and related infrastructure.

- Month 5

  - Main implementation effort: installation, configuration and initial optimisation of network, VoIP and DSP.

  - Costs are primarily labour, plus any remaining minor materials.

- Month 6

  - Focus on testing, acceptance, final tuning, documentation and training.

  - Remaining contingency is used only if needed to address approved changes or critical issues.

- Variance and control

Actual spending will be tracked against these planned amounts:

- A cost register will record commitments and actuals for each category and month.

- Variances between planned and actual spend will be reviewed regularly, and corrective actions proposed if significant differences appear.

- Use of contingency will require justification and approval in line with the cost and change management plans.

- Conclusion

This Project Budget and Cash Flow document provides a clear view of how the total budget of 184,800 AUD is allocated and when it will be used during the Darvycom Brisbane Engineering Laboratory network and DSP upgrade.

It supports realistic planning, allows early detection of cost issues and aligns with the project’s scope, schedule and cost management processes.