Project Critical Path Document

Project: Darvycom Brisbane Engineering Laboratory Network & DSP Upgrade
Prepared by: Leonardo Matias Ciarcia
Date: 16/12/2025

- Introduction

This document identifies the critical path for the Darvycom Brisbane Engineering Laboratory Network and Digital Signal Processing (DSP) upgrade. The critical path is the longest sequence of dependent activities that determines the minimum duration of the project. Any delay on a critical-path activity will delay the overall project finish date unless corrective action is taken.

The project schedule is based on a 24-week timeframe and the macro task list and Gantt chart already prepared for this project.

- Method

To determine the critical path, the following steps were used:

- Group related activities into major project phases (initiation, design, procurement, implementation, testing and closure).

- Identify logical dependencies between these activities.

- Estimate durations in weeks, consistent with the Gantt chart.

- Trace the longest continuous chain of dependent tasks from project start to project completion.

- Summary of Major Activities

- A1 – Initiation and project charter

- A2 – Project Management Plan and subplans

- A3 – Stakeholder setup and kick-off meeting

- B1 – Requirements gathering and site analysis

- B2 – Project specifications and attributes

- C1 – Network architecture and logical design

- C2 – VoIP and collaboration design

- C3 – DSP design and analysis

- C4 – Consolidated design documentation and client sign-off

- D1 – Procurement and supplier selection

- D2 – Delivery, verification and lab preparation

- E1 – Network implementation (switches, router, servers)

- E2 – VoIP, video and DSP implementation

- F1 – Technical testing (network, VoIP, DSP) and user acceptance

- F2 – Training, handover and project closure

Indicative durations (in weeks), aligned with the initial Gantt chart:

- A1: 2 weeks

- A2: 3 weeks (overlapping with A1, completed by end of Week 4)

- A3: 2 weeks (completed by end of Week 4)

- B1: 2 weeks (Weeks 5–6)

- B2: 2 weeks (Weeks 6–7)

- C1: 2 weeks (Weeks 7–8)

- C2: 2 weeks (Weeks 8–9)

- C3: 2 weeks (Weeks 9–10)

- C4: 2 weeks (Weeks 10–11)

- D1: 2 weeks (Weeks 12–13)

- D2: 2 weeks (Weeks 14–15)

- E1: 2 weeks (Weeks 16–17)

- E2: 2 weeks (Weeks 18–19)

- F1: 3 weeks (Weeks 20–22)

- F2: 2 weeks (Weeks 23–24)

- Critical Path Identification

Based on dependencies and durations, the main critical path for the project is:

A1 → A2 → A3 → B1 → B2 → C1 → C2 → C3 → C4 → D1 → D2 → E1 → E2 → F1 → F2

In words, the critical path runs through:

- Initiation and planning

- Requirements and site analysis

- Network and DSP high-level design and approval

- Procurement and delivery

- Network and VoIP/DSP implementation

- Testing, user acceptance, training and closure

This chain represents the longest, continuous sequence of dependent tasks from project start to final handover. It spans the full 24 weeks of the schedule. Other activities (for example detailed internal reviews or parallel documentation tasks) are planned to run in parallel with these tasks and therefore have some float, so they are not on the critical path.

- Impact on Project Management

Because these activities form the critical path:

- Any delay in a critical-path task will delay the overall project finish unless time is recovered elsewhere.

- Progress on critical-path activities must be closely monitored in status meetings and reports.

- If schedule pressure increases, acceleration options (such as overlapping design and procurement or adding resources during implementation) should be evaluated first for these tasks.

- Changes affecting cost, scope or resourcing of critical-path tasks must be carefully assessed for schedule impact as part of the change management process.

- Conclusion

The identified critical path provides a clear view of the activities that determine the total duration of the Darvycom Brisbane Engineering Laboratory Network and DSP upgrade project. By focusing monitoring and control efforts on this sequence of tasks, the project team can better protect the planned completion date and manage schedule-related risks throughout the project lifecycle.