# PROJECT MANAGEMENT PLAN (PMP)

Project: Darvycom Brisbane Engineering Laboratory Network & DSP Upgrade
Project Manager:  Leonardo Matias Ciarcia
Date: 19/12/2025

1. Executive Summary

Darvycom Australia is upgrading the Engineering Laboratory network in Brisbane to support its role as a regional office and to improve the quality and reliability of voice and data communications. The current environment uses copper-based telephony and a basic data network. Staff have reported poor voice quality and limited flexibility for growing client and engineering demands.

This project will design and implement an integrated IP-based network and communications solution for the two laboratory blocks in Brisbane, including VoIP, video conferencing and improved digital signal processing (DSP) to increase signal-to-noise ratio and overall call quality.

The upgraded solution will provide:

- Twenty IP phones using VoIP

- Twenty computers with updated operating systems and softphone capability

- Forty headsets with microphone

- One video conferencing system

- Two data servers

- One voice server

- One router with VPN capability

- Four managed switches

- A tuned DSP configuration integrated into the communication chain

The project will be delivered over approximately six months, using a structured project management approach. The approved baseline budget is 184,800 AUD. This plan describes the scope, methodology, work breakdown, schedule, cost and budget, risk management, quality management, communication, procurement and monitoring and control approach for the project.

2. Scope Statement

2.1 Objectives

The objectives of the project are to:

- Replace the existing copper-based telephony system with an IP-based voice solution that delivers consistent, high-quality voice services.

- Upgrade the laboratory network in both blocks to support current and future voice, data and video requirements.

- Implement an improved DSP configuration that enhances signal quality and reduces noise in communications, aligned with Darvycom’s performance targets.

- Provide secure connectivity between the Brisbane laboratory and Darvycom’s wider network using VPN.

- Enable laboratory staff to use the new network and communication services effectively through training and clear documentation.

2.2 In Scope

The project scope includes:

- Network architecture and logical design for the Brisbane laboratory (two blocks).

- Design and implementation of:

  - One VPN-capable router

  - Four managed switches

  - Two data servers

  - One voice server providing IP-PBX functionality

  - Twenty IP phones and forty headsets

  - One video conferencing system

- DSP analysis, design, simulation, configuration and integration into the voice and network environment.

- Development of required management documents and subplans.

- Network, voice, DSP and user acceptance testing.

- User training and handover to Darvycom operations.

2.3 Out of Scope

The project does not include:

- Major network or telephony changes at other Darvycom sites.

- Full replacement of all end-user computing equipment beyond the twenty specified systems.

- Organisation-wide process redesign unrelated to operating the upgraded laboratory network and communication systems.

2.4 Key Deliverables

- Approved network architecture and logical design document

- Approved DSP design and configuration document

- Project management and subplan documentation

- Installed and configured router, switches, servers, IP phones, headsets and video conferencing system

- Implemented and tuned DSP configuration integrated with the voice platform

- Test plans and test reports (network, voice, DSP and user acceptance)

- User guides, technical documentation and updated configuration records

- Completed training sessions for laboratory staff

- Project closure report with lessons learned

3. Project Methodology

The project uses a hybrid approach:

- A predictive lifecycle for network and infrastructure work, structured into phases:

  - Initiation and planning

  - Requirements and analysis

  - Design

  - Procurement and preparation

  - Implementation and integration

  - Testing and acceptance

  - Training, handover and closure

- An iterative approach for DSP work:

  - Define DSP performance objectives and constraints

  - Design candidate DSP configurations and filter parameters

  - Simulate and test configurations against analytical expectations

  - Select and refine the final configuration and integrate it with the live environment

Project management processes for scope, schedule, cost, quality, communication, human resources, risk, procurement, change, configuration and process improvement are described in dedicated subplans and are applied consistently throughout the project.

4. Work Breakdown Structure (WBS)

Level 1 – Project: Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade

- Initiation and Planning
1.1 Develop project charter
1.2 Develop Project Management Plan and subplans
1.3 Identify stakeholders and develop communication approach
1.4 Conduct project kick-off meeting

- Requirements and Analysis
2.1 Review existing documentation and current environment
2.2 Conduct site visit and assess existing network and telephony setup
2.3 Develop project specifications and attributes document (existing vs required)
2.4 Confirm detailed network and telephony requirements with client
2.5 Confirm DSP performance and quality requirements

- Design
3.1 Develop high-level network topology for both blocks
3.2 Develop logical network design (IP addressing, VLANs, routing, QoS, VPN)
3.3 Design VoIP, voice server and video conferencing solution
3.4 Analyse current DSP behaviour and limitations
3.5 Design candidate DSP configurations and simulation approach
3.6 Develop preliminary design options and assess high-level alternatives
3.7 Select recommended network and DSP option and prepare consolidated design documentation
3.8 Obtain client review and approval of consolidated design

- Procurement and Preparation
4.1 Finalise bill of materials for hardware and software
4.2 Obtain quotations and refine cost plan
4.3 Gain sponsor approval for procurement
4.4 Place purchase orders
4.5 Receive and verify equipment and licences
4.6 Prepare laboratory environment (racks, power, UPS and cabling)
4.7 Update configuration management database with new assets

- Implementation and Integration
5.1 Install and configure managed switches in both blocks
5.2 Install and configure VPN-capable router
5.3 Install and configure data servers
5.4 Install and configure voice server and initial dial plan
5.5 Deploy IP phones and headsets to staff locations
5.6 Install and configure video conferencing system
5.7 Configure VLANs, QoS, routing and VPN
5.8 Implement selected DSP configuration in the laboratory environment
5.9 Integrate DSP with voice platform and network

- Testing and Acceptance
6.1 Develop detailed test plans (network, voice, DSP and user acceptance)
6.2 Conduct network performance and connectivity tests
6.3 Conduct voice and call quality tests
6.4 Conduct DSP performance tests (including signal-to-noise ratio and stability)
6.5 Conduct user acceptance testing with laboratory staff
6.6 Resolve defects and issues and retest as required
6.7 Obtain final acceptance and sign-off from the client

- Training, Handover and Closure
7.1 Develop user guides and technical documentation
7.2 Deliver training to laboratory staff
7.3 Handover documentation and configuration records to operations
7.4 Final project review and lessons learned
7.5 Project closure and archiving of records

5. Project Schedule

The planned duration of the project is approximately six months. Activities are scheduled in a logical sequence and aligned with the critical path identified for the project.

Summary schedule by phase:

- Month 1

  - Initiation and planning

  - Project charter, Project Management Plan and subplans

  - Stakeholder identification and kick-off

- Month 2

  - Requirements and analysis

  - Site visit, existing network assessment

  - Project specifications and confirmation of network and DSP requirements

- Months 2–4

  - Network and DSP design

  - High-level and logical design for network, VoIP and video

  - DSP analysis, candidate designs and preliminary design options

  - Consolidated design documentation and client approval

- Months 4–5

  - Procurement and preparation

  - Finalisation of bill of materials and cost plan

  - Supplier selection, purchase orders and delivery

  - Laboratory preparation and initial asset registration

- Months 5–6

  - Implementation and integration

  - Installation and configuration of network and voice infrastructure

  - Implementation and integration of the selected DSP configuration

- Month 6

  - Testing and acceptance

  - Technical testing (network, voice, DSP) and user acceptance testing

  - Defect resolution, training, handover and closure

The critical path runs through initiation and planning, requirements and analysis, design and approval, procurement and delivery, implementation and integration, testing and acceptance, and final handover. Non-critical documentation tasks are planned to run in parallel and have float, but critical-path activities are monitored closely to protect the planned completion date.

6. Cost Plan and Budget

The approved baseline budget for the project is 184,800 AUD. This budget aligns with the final design option and covers the full scope of work.

Budget structure:

- Network hardware: 40,000 AUD

  - Managed switches, router, IP phones, headsets and video conferencing system

- Servers and voice platform: 34,000 AUD

  - Two data servers

  - One voice server

- Software and licences: 20,000 AUD

  - Operating systems and server licences

  - Voice platform software

  - Monitoring and management tools

  - DSP tools and related software

- Infrastructure, racks and UPS: 12,000 AUD

  - Racks, patch panels, structured cabling and UPS adjustments

- Implementation and configuration services: 25,000 AUD

  - Network, voice and DSP implementation work

  - Support during cutover and stabilisation

- Project management, documentation and training: 23,000 AUD

  - Planning, coordination, reporting

  - Documentation, user guides and training sessions

- Contingency: 30,800 AUD

  - Held centrally to address approved changes and unforeseen cost pressures

Total baseline budget: 184,800 AUD

Cash flow is spread across the six-month period, with the highest expenditure during procurement and implementation. Costs are tracked against this baseline and managed through the cost management processes described in the Cost Management Plan and Budget Management Plan.

7. Risk Management Plan

Risks are identified, analysed and managed throughout the project. Key risk areas include:

- Requirements and design

  - Risk: Incomplete or ambiguous requirements leading to redesign or rework.

  - Response: Early engagement with stakeholders, clear documentation of specifications and attributes, and formal design review and sign-off.

- Technical and integration

  - Risk: Network or voice configuration issues impacting performance or reliability.

  - Risk: DSP configuration not achieving expected signal quality improvements.

  - Response: Use of staged implementation, configuration management, thorough testing and the ability to adjust DSP parameters based on measured results.

- Procurement and schedule

  - Risk: Late delivery of critical hardware or software delaying implementation.

  - Response: Early procurement planning, alternative suppliers where possible, and regular monitoring of delivery schedules.

- Operational and change

  - Risk: Disruption to laboratory operations during installation and cutover.

  - Response: Careful scheduling of implementation, clear communication with users and defined rollback plans if issues occur.

8. Quality Management Plan

Quality objectives:

- Deliver a stable, high-performance network infrastructure supporting both blocks.

- Provide high-quality VoIP calls and reliable video conferencing.

- Achieve a measurable improvement in signal quality through the DSP solution.

- Provide documentation and training that allow staff to operate and support the environment confidently.

Quality approach:

- Use agreed design and configuration standards for network and voice systems.

- Develop and execute test plans covering connectivity, performance, voice quality and DSP behaviour.

- Use quality metrics such as call quality indicators, network performance statistics, and pass/fail results from defined test cases.

- Record defects, corrective actions and retest outcomes in test reports.

Quality assurance and control activities are coordinated with the testing phase and are supported by the Quality Management Plan.

9. Communication Plan

Communication objectives:

- Ensure stakeholders understand the project’s progress, risks and decisions.

- Provide clear information about planned changes and their impact on the laboratory.

- Support smooth coordination within the project team and with Darvycom operations.

Key communication activities:

- Regular project status updates, including progress, risks and cost status.

- Design reviews and approval meetings with client representatives.

- Implementation and cutover notices to affected staff, including timing and impact.

- Training sessions and handover briefings for operations staff.

10. Procurement Plan

Procurement scope:

- Network devices (router, switches, cabling components)

- Servers and voice platform equipment

- IP phones, headsets and video conferencing system

- Software licences and tools required for network management and DSP

Procurement approach:

- Finalise bill of materials based on the approved design.

- Obtain quotations from suitable suppliers that meet Darvycom’s standards.

- Evaluate suppliers on cost, delivery time, support and compliance.

- Seek sponsor approval for the recommended procurement package.

- Place purchase orders and monitor delivery.

- Verify deliveries and update asset and configuration records.

Procurement activities follow Darvycom’s procurement policies and are coordinated with the Budget Management Plan and Cost Management Plan.

11. Monitoring and Control Plan

Monitoring and control ensure that the project remains aligned with its scope, time, cost and quality objectives.

Key elements:

- Schedule control

  - Track progress against the baseline schedule and critical path.

  - Adjust resourcing or sequencing when slippage is identified.

- Cost control

  - Track commitments and actual costs against the cost baseline.

  - Review variances and recommend corrective actions, including controlled use of contingency where required.

- Scope and change control

  - Evaluate changes for impact on scope, schedule, cost and risk.

  - Use formal change requests and the change management process for approval.

  - Update plans and documentation after changes are approved.

- Quality control

  - Use defined acceptance criteria and test plans to validate deliverables.

  - Record and resolve defects in a structured way.

- Risk and issue management

  - Maintain and review the risk register and issues log.

  - Implement agreed mitigation and contingency actions.