Project Schedule (Task List)
Project: Darvycom Brisbane Engineering Laboratory Network & DSP Upgrade
Prepared by: Leonardo Matias Ciarcia
Date: 15/12/2025

1. Initiation and Planning

1.1 Develop Project Charter and high-level scope

- Define project objectives, high-level scope, constraints and success criteria.

- Planned timing: Month 1

1.2 Develop Project Management Plan and subplans

- Complete PMP and core subplans (Scope, Schedule, Cost, Quality, HR, Communication, Procurement, Change, Configuration, Process Improvement, Requirements, Risk).

- Planned timing: Month 1

1.3 Stakeholder setup and kick-off meeting

- Identify stakeholders, agree on communication approach, and hold formal kick-off meeting with Darvycom.

- Planned timing: Month 1

2. Requirements and Analysis

2.1 Site visit and current network assessment

- Review existing infrastructure in both lab blocks and document current phones, computers, servers, switches, router and cabling.

- Planned timing: Early Month 2

2.2 Confirm network and DSP requirements

- Confirm expected network, VoIP, video conferencing, server and DSP requirements with the client and document “project specifications and attributes”.

- Planned timing: Month 2

3. Design

3.1 Network architecture and logical design

- Produce the overall network topology, IP addressing, VLANs, routing, QoS and VPN design for both blocks.

- Planned timing: Late Month 2 – Early Month 3

3.2 VoIP and collaboration design

- Design IP telephony, voice server configuration, extension plan, and integration with the video conferencing system.

- Planned timing: Month 3

3.3 DSP design and analysis

- Define DSP objectives, analyse current signal issues, design candidate DSP configurations and select the preferred solution.

- Planned timing: Month 3 – Month 4

3.4 Design documentation and approval

- Compile design documentation (network + DSP) and obtain formal client approval.

- Planned timing: End of Month 4

4. Procurement and Preparation

4.1 Finalise bill of materials and cost plan

- Confirm hardware and software list, refine costs and align with the approved project budget.

- Planned timing: Early Month 4

4.2 Supplier selection and purchasing

- Select suppliers, issue purchase orders and confirm delivery dates for all equipment and licences.

- Planned timing: Month 4

4.3 Delivery, verification and environment preparation

- Receive and check equipment, update asset/configuration records, and prepare racks, power and cabling in the lab.

- Planned timing: Late Month 4 – Early Month 5

5. Implementation and Integration

5.1 Network deployment

- Install and configure switches, router, data servers and core network services across both blocks.

- Planned timing: Month 5

5.2 VoIP and collaboration deployment

- Install and configure voice server, IP phones, headsets and video conferencing system.

- Planned timing: Month 5

5.3 DSP implementation and integration

- Implement the selected DSP configuration and integrate it into the communication chain with the upgraded network and voice platform.

- Planned timing: Late Month 5 – Early Month 6

6. Testing and Acceptance

6.1 Technical testing

- Execute tests for network performance, call quality, VPN operation and DSP behaviour (including SNR and stability).

- Planned timing: Month 6

6.2 User acceptance testing

- Conduct user-based testing with laboratory staff and capture feedback on usability and performance.

- Planned timing: Month 6

6.3 Defect resolution and final acceptance

- Fix issues, re-test as needed and obtain formal acceptance from the client for the full solution.

- Planned timing: End of Month 6