DOCUMENT INFORMATION

| ID | 012025SMP |
| --- | --- |
| OWNER | DARVYCOM AUSTRALIA PTY LTD |
| PROJECT NAME | Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade |
| ISSUE DATE | 15/12/2025 |
| LAST DATE SAVED | 02.02.2026 |
| VERSION | 1.1 |
| APPROVAL OF SPONSOR |  |

This template provides a guide for you to complete the SCHEDULE MANAGEMENT PLAN

for the Darvycom Australia Pty Ltd project of cluster 6 of the ADIT TNE programme. Please refer to the project scenario of Tasks3 and 4 of Cluster 6 project for details regarding all aspects of this plan. Ensure you provide all relevant details for your final report before submission.

Table of Contents

SCHEDULE METHODOLOGY AND TECHNIQUE:	3

SOFTWARE FOR SCHEDULING:	4

MEASUREMENT COMPONENTS:	5

SUCCESSFUL SCHEDULE IMPLEMENTATION	6

ACCEPTABLE TOLERANCES	7

CONTIGENCY LEVERAGING /TOLERANCES:	8

PROGRESS MANAGEMENT	9

PROJECT SCHEDULE	10

# SCHEDULE METHODOLOGY AND TECHNIQUE:

The Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade will use a predictive schedule-management approach. The project scope has been divided into defined tasks with planned start weeks, finish weeks, durations and dependencies. The approved schedule covers 24 weeks, approximately six months.

The Work Breakdown Structure is used to organise the project into the following main phases:

- Initiation and project planning

- Requirements and current-network analysis

- Network, voice, wireless, video and DSP design

- Procurement and laboratory preparation

- Network 3 implementation and integration

- Integrated testing and user acceptance

- Training, handover and project closure

A Gantt chart is used to display the timing and relationship between the tasks. Activities may overlap where appropriate. For example, requirements confirmation and project specifications overlap during Weeks 6–7, while the network, voice and DSP design activities are coordinated before final design approval.

The critical sequence begins with project initiation and continues through requirements, design approval, procurement, implementation, testing, acceptance and closure. A delay to a critical activity may affect the final Week 24 completion date.

The schedule will be controlled through:

- Task dependencies and milestone dates

- Weekly progress monitoring

- Comparison of planned and actual progress

- Identification of schedule variances

- Corrective actions for delayed activities

- Formal approval of significant schedule changes

- Updating the Gantt chart after approved changes

# SOFTWARE FOR SCHEDULING:

The Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade will use a predictive schedule-management approach. The project scope has been divided into defined tasks with planned start weeks, finish weeks, durations and dependencies. The approved schedule covers 24 weeks, approximately six months.

The Work Breakdown Structure is used to organise the project into the following main phases:

- Initiation and project planning

- Requirements and current-network analysis

- Network, voice, wireless, video and DSP design

- Procurement and laboratory preparation

- Network 3 implementation and integration

- Integrated testing and user acceptance

- Training, handover and project closure

A Gantt chart is used to display the timing and relationship between the tasks. Activities may overlap where appropriate. For example, requirements confirmation and project specifications overlap during Weeks 6–7, while the network, voice and DSP design activities are coordinated before final design approval.

The critical sequence begins with project initiation and continues through requirements, design approval, procurement, implementation, testing, acceptance and closure. A delay to a critical activity may affect the final Week 24 completion date.

The schedule will be controlled through:

- Task dependencies and milestone dates

- Weekly progress monitoring

- Comparison of planned and actual progress

- Identification of schedule variances

- Corrective actions for delayed activities

- Formal approval of significant schedule changes

- Updating the Gantt chart after approved changes

# MEASUREMENT COMPONENTS:

Project progress will be measured against the approved 24-week schedule baseline.

| Measurement component | Method of measurement | Required response |
| --- | --- | --- |
| Task completion | Compare completed work with the task requirements | Confirm that all outputs for the task have been produced |
| Planned versus actual start | Compare the actual start week with the Gantt chart | Investigate late starts that may affect dependent tasks |
| Planned versus actual finish | Compare the actual completion week with the planned finish | Record and explain schedule variance |
| Duration variance | Calculate actual duration minus planned duration | Apply corrective action when tolerance is exceeded |
| Percentage complete | Record the estimated percentage of work completed | Update during weekly progress reviews |
| Milestone achievement | Check whether phase approvals were obtained on time | Escalate missed critical milestones |
| Dependency status | Confirm predecessor tasks are complete | Do not begin dependent work without required inputs |
| Schedule Performance Index | Compare earned progress with planned progress | Investigate an SPI below 1.00 |
| Forecast completion | Estimate when remaining work will finish | Raise a change request if Week 24 is at risk |
| Issue resolution time | Measure the time required to resolve schedule issues | Escalate issues that remain unresolved beyond the agreed period |

Important milestones include:

- Project planning and kick-off completed by Week 4

- Requirements and component analysis completed by Week 7

- Final Network 3 design approved by Week 11

- Procurement and laboratory preparation completed by Week 15

- Network 3 infrastructure implemented by Week 17

- VoIP, wireless, video, PRTG and DSP setup completed by Week 19

- Integrated testing and UAT completed by Week 22

- Training, handover and closure completed by Week 24

# SUCCESSFUL SCHEDULE IMPLEMENTATION

Successful schedule implementation requires the project team to understand the planned activities, assigned responsibilities, dependencies and expected deliverables.

The following controls will support successful implementation:

- The Project Manager will maintain the approved schedule.

- Team members will report progress and issues during weekly reviews.

- Required resources will be confirmed before each activity begins.

- Technical tasks will not begin until their required predecessor activities are completed.

- Network, voice, wireless, security, monitoring and DSP activities will be coordinated.

- Hardware and licences will be ordered early enough to reduce delivery risk.

- Equipment will be inspected before implementation.

- Technical configurations will be backed up before major changes.

- Network 3 will be implemented in planned stages.

- Connectivity and service tests will be conducted after configuration.

- Failed tests will be corrected and repeated.

- Schedule risks will be recorded in the risk register.

- Significant schedule changes will follow the change-control procedure.

- Updated documents will reflect the final implementation.

- Client approval will be obtained before final closure.

Communication between the Project Manager, technical team, suppliers and Darvycom representatives is necessary to prevent delays. Problems affecting procurement, configuration, DSP performance, testing or access to the laboratory must be reported promptly.

# ACCEPTABLE TOLERANCES

The following schedule tolerances will apply:

| Schedule area | Acceptable tolerance | Required action when exceeded |
| --- | --- | --- |
| Individual non-critical task | Up to five working days, provided no later activity is affected | Project Manager may reorganise work within the existing phase |
| Critical-path task | No unapproved delay | Immediate review and corrective action |
| Phase milestone | Up to five working days if Week 24 remains achievable | Record the reason and revise the short-term work plan |
| Overall project completion | Completion must remain within 24 weeks | Sponsor approval required for any extension |
| Resource availability | Minor temporary variation that does not delay a milestone | Reallocate available resources |
| Supplier delivery | Delay manageable within the procurement and preparation period | Contact supplier or use an approved alternative |
| Schedule Performance Index | 0.95 or higher | Investigate and correct performance below 0.95 |
| Schedule-related cost impact | Must remain within the approved budget and authority limits | Follow the Budget Management Plan and change procedure |

Any delay greater than five working days, any impact on the critical path or any forecast completion beyond Week 24 must be escalated to the Project Sponsor.

A formal change request is required when a proposed schedule change:

- Changes the final completion date

- Changes an approved milestone

- Creates a material budget impact

- Requires additional resources or procurement

- Changes the approved Network 3 scope

- Affects client acceptance or operational handover

# CONTIGENCY LEVERAGING /TOLERANCES:

No separate unapproved time allowance will be added to the official 24-week schedule. Schedule contingency will be managed by using recovery actions within the existing project phases.

Available contingency actions include:

- Reprioritising non-critical activities so the critical work can continue.

- Performing documentation, training preparation and test planning in parallel with technical activities.

- Using an approved alternative supplier when equipment delivery is delayed.

- Reallocating technical personnel to a delayed critical activity.

- Staging the Network 3 implementation so completed components can be configured and tested while other equipment is prepared.

- Using backup configurations and rollback procedures if an implementation change fails.

- Completing preliminary Packet Tracer and DSP simulations before physical implementation.

- Conducting failed-test correction and retesting during the Week 20–22 testing period.

- Using approved financial contingency only in accordance with the Budget Management Plan.

- Raising a formal change request when the completion target cannot be maintained.

The Project Manager must assess the effect of a contingency action on scope, cost, quality, security and other scheduled tasks before authorising it. Contingency actions must not remove required testing, security configuration, documentation, user acceptance or client approval activities.

# PROGRESS MANAGEMENT

Progress will be reviewed weekly and formally reported monthly. The Project Manager will update the schedule using information received from the technical team, suppliers and project stakeholders.

The weekly review will record:

- Tasks planned for the reporting period

- Tasks completed

- Current percentage complete

- Actual start and completion dates

- Tasks delayed or at risk

- Dependency status

- Resource or supplier problems

- Corrective actions

- Responsible action owners

- Forecast completion dates

Monthly reporting will compare the current project position against the approved schedule baseline. The report will include milestone status, significant variances, risks, approved changes and the forecast Week 24 completion date.

Technical progress will be supported by evidence such as:

- Approved project requirements and specifications

- Network 1 assessment records

- Final Network 3 design and IP schema

- Packet Tracer configuration and test results

- Cisco CME/IP-phone registration and call tests

- Wireless and video connectivity tests

- Firewall, VPN and inter-VLAN routing tests

- PRTG availability and performance evidence

- DSP spectrum, Fourier and convolution analysis

- User acceptance results

- Training and handover records

Schedule status may be reported using:

- Green: Task is on schedule

- Amber: Task is at risk or has a manageable delay

- Red: Task is delayed and may affect a milestone or Week 24 completion

When a task is amber or red, the Project Manager will document the cause, corrective action, responsible person and required completion date.

# PROJECT SCHEDULE

Use this updated table in the final section.

| Task ID | Task name | Start week | End week | Duration | Main dependency |
| --- | --- | --- | --- | --- | --- |
| 1 | Initiation and project charter | 1 | 2 | 2 weeks | None |
| 2 | Project Management Plan and subplans | 2 | 4 | 3 weeks | Task 1 |
| 3 | Stakeholder setup and kick-off meeting | 3 | 4 | 2 weeks | Tasks 1 and 2 |
| 4 | Client requirements and current-network analysis | 5 | 6 | 2 weeks | Task 3 |
| 5 | Specifications and required-component analysis | 6 | 7 | 2 weeks | Task 4 |
| 6 | Network 3 VLAN, IP and security design | 7 | 8 | 2 weeks | Task 5 |
| 7 | VoIP, wireless and video design | 8 | 9 | 2 weeks | Task 6 |
| 8 | DSP modelling, simulation and analysis | 9 | 10 | 2 weeks | Task 5 |
| 9 | Final Network 3 design documentation and approval | 10 | 11 | 2 weeks | Tasks 6, 7 and 8 |
| 10 | Procurement, licensing and supplier selection | 12 | 13 | 2 weeks | Task 9 |
| 11 | Delivery, verification and laboratory preparation | 14 | 15 | 2 weeks | Task 10 |
| 12 | Network 3 core, VLAN, firewall and server setup | 16 | 17 | 2 weeks | Task 11 |
| 13 | VoIP/CME, WLAN, video, PRTG and DSP setup | 18 | 19 | 2 weeks | Task 12 |
| 14 | Integrated network, voice, PRTG, DSP testing and UAT | 20 | 22 | 3 weeks | Task 13 |
| 15 | Training, documentation, handover and closure | 23 | 24 | 2 weeks | Task 14 |

The project schedule covers 24 weeks and follows the approved sequence from initiation to closure. Some design activities overlap to make effective use of resources, but implementation cannot begin until the Network 3 design has been approved. Final closure depends on successful integrated testing, user acceptance, completed documentation, training and client sign-off.