REQUIREMENT MANAGEMENT PLAN

DARVYCOM AUSTRALIA PTY LTD

| ID | C6-RMP-01 |
| --- | --- |
| OWNER | DARVYCOM AUSTRALIA PTY LTD |
| PROJECT NAME | Brisbane Engineering Laboratory Network and DSP Upgrade |
| ISSUE DATE | 12/11/2025 |
| LAST DATE SAVED | 12/11/2025 |
| VERSION | 1.0 |
| APPROVAL OF SPONSOR |  |

This template provides a guide for you to complete the REQUIREMENT MANAGEMENT PLAN

for the Darvycom Australia Pty Ltd project of cluster 6 of the ADIT TNE programme. Ensure you provide all relevant details for your final report before submission. Please refer to the project scenario of Tasks3 and 4 of Cluster 6 project for details regarding all aspects of this plan.

Table of Contents

INTRODUCTION	3

PURPOSE	4

REQUIREMENT GATHERING PROCESS	5

TYPES OF REQUIREMENTS AND RESPONSBILITIES	6

TRACEABILITY MATRIX TEMPLATE	7

ASSUMPTIONS AND CONSTRAINTS	8

VALIDATION AND VERIFICATION OF THE REQUIREMENTS	9

CHANGE MANAGEMENT PROCESS	10

CONCLUSION	11

# INTRODUCTION

Darvycom Australia Pty Ltd is upgrading the communications and data network used by the Brisbane Engineering Laboratory in Blocks A and B. The existing environment relies on separate small networks, legacy analogue telephony and limited central monitoring.

The selected Network 3 solution introduces a secure, reliable and centrally managed architecture consisting of:

- Internet Service Provider connection

- VPN router

- Firewall

- Layer 3 core switch

- Four managed Power over Ethernet access switches

- Wireless access points

- Cisco 2911 CME/IP-PBX router

- PRTG Network Monitor

- UPS protection

The project scope includes 20 computers, 20 IP phones, 40 compatible headsets, one video-conferencing endpoint and two data servers.

Logical network separation will be provided using VLANs 10, 20, 30, 40, 50, 60, 110, 120 and 130. Quality of Service will be implemented to prioritise voice and video communications.

This Requirement Management Plan explains how requirements will be gathered, recorded, reviewed, prioritised, approved, traced, validated, verified and controlled throughout the 24-week project.

The approved project budget baseline used in this plan is AUD 184,800. Any proposal to use another budget amount or change the approved scope, schedule, architecture or acceptance criteria must be processed through formal change control.

# PURPOSE

The purpose of this plan is to ensure that the Darvycom Network and DSP Upgrade remains aligned with the client’s requirements from project initiation through implementation and handover.

The plan will:

- Establish an approved requirements baseline.

- Identify business, functional, technical and non-functional requirements.

- Assign ownership and approval responsibilities.

- Link each requirement to its design component and verification evidence.

- Prevent uncontrolled changes to scope.

- Define how requirements will be validated and verified.

- Support accessible documentation, training and operational handover.

- Ensure simulated, representative and production evidence are clearly distinguished.

## In scope

Requirements management covers:

- Network 3 architecture

- Wired and wireless access

- VLAN and IP addressing

- Inter-VLAN routing

- Firewall and access-control rules

- VPN services

- IP telephony

- Video conferencing

- Data-server connectivity

- QoS

- PRTG monitoring

- UPS and recovery arrangements

- DSP analysis

- Testing and evidence

- Documentation and training

- Operational handover

## Out of scope

The following are excluded unless formally approved:

- Business applications unrelated to the laboratory network

- ISP infrastructure outside Darvycom’s responsibility

- Deployment at other Darvycom locations

- Unapproved equipment substitutions

- Additional users or devices outside the agreed quantities

# REQUIREMENT GATHERING PROCESS

Requirements will be gathered progressively and baselined before procurement or implementation. Informal stakeholder requests must be converted into clear and testable requirements.

## Information sources and gathering methods

Requirements will be collected from:

- The Darvycom project scenario and client brief

- Existing-network resource information

- Preliminary and detailed network designs

- Project budget and implementation schedule

- Interviews with the project sponsor and laboratory users

- Discussions with network-support and security personnel

- Site surveys of Blocks A and B

- Existing network and traffic observations

- Supplier specifications and compatibility information

- Packet Tracer simulations

- PRTG monitoring observations

- MATLAB and Academo DSP activities

- User acceptance and training feedback

## Controlled gathering workflow

- Identify the stakeholder, business outcome and source of the requirement.

- Assign the requirement a unique identification number.

- Record its description, rationale, owner, priority and acceptance criteria.

- Confirm that it is specific, measurable, achievable, relevant and testable.

- Remove duplicated or conflicting requirements.

- Classify the requirement as Must have, Should have, Could have or Won’t have for this release.

- Assess technical feasibility, security, accessibility, cost, schedule, supplier and risk impacts.

- Review the requirement with affected stakeholders.

- Obtain the appropriate approval.

- Add the approved requirement to the requirements register and traceability matrix.

- Baseline the approved register.

- Process subsequent modifications through the Change Management Process.

# TYPES OF REQUIREMENTS AND RESPONSBILITIES

## Requirement categories

| Type | Purpose | Darvycom example |
| --- | --- | --- |
| Business | Defines the required organisational outcome and project limits. | Upgrade the laboratory network within 24 weeks and the AUD 184,800 baseline. |
| Stakeholder | Defines what users, the sponsor and support teams require. | Reliable connectivity in both blocks and usable support documentation. |
| Functional | Defines what the solution must do. | Connect computers, register IP phones, provide VPN, wireless, video and monitoring. |
| Technical | Defines architecture, standards and configuration. | Network 3 topology, VLANs, IP addressing, Layer 3 switching, firewall and Cisco CME. |
| Non-functional | Defines quality, performance, security and availability. | Gigabit uplinks, QoS, monitoring, UPS protection and recoverability. |
| DSP | Defines digital-signal-processing analysis. | Spectrum analysis and linear and circular convolution. |
| Transition | Defines implementation and handover needs. | Staged cutover, backups, rollback, training and documentation. |
| Compliance and accessibility | Defines privacy, legal and inclusive-access considerations. | Protected monitoring logs and accessible documentation and dashboards. |
| Acceptance | Defines the evidence required for approval. | Successful connectivity, calls, monitoring, DSP results and stakeholder sign-off. |

## Roles and responsibilities

| Role | Requirement responsibilities | Authority |
| --- | --- | --- |
| Project sponsor | Confirms the business need, funding and final acceptance. | Approves major scope, budget or schedule changes. |
| Project Manager – Leonardo Matias Ciarcia | Maintains the requirements register and traceability matrix and coordinates reviews. | Owner of the requirements baseline. |
| Technical/network specialist | Converts requirements into architecture, security, capacity and configuration specifications. | Provides technical recommendations. |
| Voice specialist | Defines IP-phone registration, dial plans, QoS and call-testing requirements. | Provides voice-system verification. |
| DSP specialist | Defines DSP inputs, methods, expected outputs and evidence. | Provides DSP verification. |
| Laboratory users | Explain operational needs and participate in usability and acceptance testing. | Provide user validation. |
| IT/network support | Reviews monitoring, maintenance, backups, security and handover requirements. | Provides operational acceptance. |
| Supplier/vendor | Confirms specifications, compatibility, warranty and delivery information. | Provides product-compliance evidence. |
| Security/accessibility reviewer | Reviews privacy, cybersecurity and accessibility requirements. | Provides independent review. |
| Project sponsor | Completes final project acceptance. | Final approval. |

## Approved requirements register

| ID | Type | Requirement | Priority |
| --- | --- | --- | --- |
| BR-01 | Business | Upgrade the Blocks A and B laboratory network to a secure, reliable and centrally managed solution. | Must |
| BR-02 | Business | Deliver the approved scope within 24 weeks and the AUD 184,800 baseline. | Must |
| FR-01 | Functional | Provide managed network connectivity for 20 computers across both laboratory blocks. | Must |
| FR-02 | Functional | Provide 20 IP phones using Cisco 2911 CME/IP-PBX services and 40 compatible headsets. | Must |
| FR-03 | Functional | Provide one video-conferencing endpoint with end-to-end connectivity. | Must |
| FR-04 | Functional | Provide controlled connectivity for two data servers. | Must |
| FR-05 | Functional | Provide authenticated and encrypted VPN access for authorised users. | Must |
| FR-06 | Functional | Provide wireless access using approved SSIDs and security settings. | Should |
| TR-01 | Technical | Implement the ISP–VPN router–firewall–Layer 3 core–four PoE switch architecture. | Must |
| TR-02 | Technical | Implement VLANs 10, 20, 30, 40, 50, 60, 110, 120 and 130 with documented IP addressing. | Must |
| TR-03 | Technical | Apply QoS classification and priority treatment to voice and video traffic. | Must |
| TR-04 | Technical | Implement PRTG monitoring for reachability, traffic, health, availability and alarms. | Must |
| NFR-01 | Performance | Provide Gigabit uplinks and capacity above the estimated 66.18 Mbit/s planning demand. | Must |
| NFR-02 | Security | Use firewall rules, VLAN separation, least-privilege access and configuration backups. | Must |
| NFR-03 | Availability | Provide UPS support, monitoring and documented recovery and rollback procedures. | Should |
| DSP-01 | DSP | Evaluate Fourier and spectrum analysis using time-domain and frequency-domain views. | Must |
| DSP-02 | DSP | Evaluate linear and circular convolution in MATLAB. | Must |
| DOC-01 | Transition | Provide diagrams, IP plans, configurations, tests, training and handover records. | Must |
| ACC-01 | Accessibility | Provide accessible documentation and alternatives for dashboards, telephony, video and support access. | Should |

# TRACEABILITY MATRIX TEMPLATE

| ID | Design or deliverable | Verification evidence | Owner | Current status |
| --- | --- | --- | --- | --- |
| BR-01 | Approved Network 3 design and implementation package | Design approval and final acceptance | Project Manager | Approved |
| BR-02 | 24-week schedule and AUD 184,800 baseline | Schedule and budget review | Project Manager | Approved |
| FR-01 | PC access ports and data VLAN addressing | IP settings and connectivity tests | Network specialist | Tested in model |
| FR-02 | 20 IP phones, 40 headsets and Cisco 2911 CME | Registration and successful-call evidence | Voice specialist | Tested in model |
| FR-03 | Video endpoint on video VLAN; reference 10.10.40.10 | Ping, application and QoS tests | Network specialist | Tested in model |
| FR-04 | Two servers on server VLAN; Server1 reference 10.10.60.10 | Reachability and authorised-access tests | Server/network support | Tested in model |
| FR-05 | VPN router, firewall policy and authorised accounts | Authentication, encryption and access tests | Security reviewer | Evidence pending |
| FR-06 | Wireless APs, SSID and security configuration | Association, coverage and access-control tests | Network specialist | Evidence pending |
| TR-01 | Network 3 architecture | Diagram and equipment review | Technical reviewer | Approved |
| TR-02 | VLAN and IP-addressing plan | VLAN, trunk, gateway and isolation tests | Network specialist | Tested in model |
| TR-03 | QoS classification and priority queues | Configuration review and controlled traffic test | Technical reviewer | Evidence pending |
| TR-04 | PRTG ping, traffic, health and alarm sensors | Dashboard, graph, alarm and report screenshots | IT/network support | Representative evidence |
| NFR-01 | Gigabit uplinks and capacity design | PRTG graph and utilisation calculation | Network specialist | Evidence pending |
| NFR-02 | Firewall, VLANs, ACLs and secure administration | Rule review, access tests and backup evidence | Security reviewer | Evidence pending |
| NFR-03 | UPS and recovery procedures | Controlled recovery and restore test | IT/network support | Evidence pending |
| DSP-01 | Academo spectrum and oscilloscope activities | Time/frequency and linear/log screenshots | DSP specialist | Evidence to attach |
| DSP-02 | MATLAB convolution activities | Scripts, outputs, plots and interpretation | DSP specialist | Evidence to attach |
| DOC-01 | Project documentation and training package | Document register and signed handover | Project Manager | In progress |
| ACC-01 | Accessible documents and communication alternatives | Accessibility review checklist | Accessibility reviewer | Evidence pending |

# ASSUMPTIONS AND CONSTRAINTS

# ASSUMPTIONS AND CONSTRAINTS

## Assumptions

- Network 3 remains the approved design.

- The scope includes 20 computers, 20 IP phones, 40 headsets, one video endpoint and two data servers.

- Internet access, suitable electrical power, rack capacity and authorised building access will be available.

- Required licences and compatible devices can be obtained within the procurement period.

- Stakeholders will be available for reviews, user acceptance testing, training and sign-off.

- Packet Tracer, MATLAB, Academo and PRTG evidence will be retained.

- Evidence will be labelled as simulated, calculated, representative or measured on site.

## Constraints

| ID | Constraint | Management response |
| --- | --- | --- |
| C-01 | The project must be completed within 24 weeks. | Freeze long-lead requirements early and escalate delays. |
| C-02 | The approved budget baseline is AUD 184,800. | Require formal approval before changing the baseline. |
| C-03 | Laboratory disruption must be minimised. | Use staged implementation, approved outage windows and rollback procedures. |
| C-04 | Existing equipment may not fully support VLAN, PoE or IP-voice features. | Perform compatibility checks before procurement and cutover. |
| C-05 | Packet Tracer and home-lab PRTG results do not prove production performance. | Complete site acceptance tests and clearly identify evidence sources. |
| C-06 | Monitoring and remote access may involve sensitive information. | Use authorised accounts, least privilege, redaction and secure evidence storage. |
| C-07 | Supplier delays or substitutions may affect the schedule. | Confirm lead times and assess substitutions through change control. |
| C-08 | Support personnel require suitable technical knowledge. | Provide training, operating procedures and supervised handover. |

# VALIDATION AND VERIFICATION OF THE REQUIREMENTS

Validation confirms that the requirements represent what Darvycom and its laboratory users need.

Verification confirms that the delivered design, configuration, equipment or documentation satisfies the approved requirement.

## Validation activities

- Review requirements with the sponsor and laboratory users.

- Compare Network 3 with the other preliminary design options.

- Demonstrate the Packet Tracer model.

- Confirm endpoint, telephony, video and cross-VLAN behaviour.

- Conduct user acceptance testing.

- Review operating and training documents with support personnel.

- Complete accessibility checks.

- Obtain stakeholder approval.

## Verification and acceptance matrix

| Test | Requirement or criterion | Evidence | Pass condition |
| --- | --- | --- | --- |
| V-01 | Twenty computers obtain approved addressing and reach authorised services. | IP settings and ping/application screenshots | No unexplained connectivity failure |
| V-02 | Twenty IP phones register with Cisco CME and complete calls. | Registration and call screenshots | Successful calls with acceptable quality |
| V-03 | The video endpoint and two servers are reachable. | Tests including 10.10.40.10 and 10.10.60.10 | Successful authorised communication |
| V-04 | VLANs, trunks, gateways, ACLs and firewall rules enforce segmentation. | Configuration review and positive/negative tests | Required traffic passes and prohibited traffic is blocked |
| V-05 | QoS protects voice and video under load. | Policy configuration and queue statistics | Voice/video stays within approved delay and loss limits |
| V-06 | VPN provides secure authorised access. | Authentication, encryption and failed-login evidence | Only authorised users and resources are accessible |
| V-07 | PRTG monitors reachability, traffic and system health. | Ping, SNMP, health, alarm and report screens | Sensors poll correctly and alarms are recorded |
| V-08 | Network performance provides adequate capacity. | PRTG graphs and 66.18 Mbit/s comparison | No sustained bottleneck |
| V-09 | Recovery and rollback procedures are workable. | Configuration backup, UPS and restore timestamps | Service returns within the agreed recovery target |
| V-10 | Spectrum analysis produces understandable results. | Academo spectrum and oscilloscope screenshots | Dominant frequencies and noise can be identified |
| V-11 | Linear and circular convolution are correctly calculated. | MATLAB scripts, outputs and plots | Results match expected sequences |
| V-12 | Documentation and training are complete and accessible. | Document register, checklist and attendance record | Support personnel can operate and recover the solution |

## Defect and acceptance handling

A failed test must be recorded as a defect linked to the applicable requirement ID. The record must include:

- Description of the failure

- Defect severity

- Cause

- Corrective action

- Responsible person

- Target date

- Retest result

Critical and high-severity defects prevent final acceptance. Medium and low defects may only remain open when an owner, completion date and sponsor decision have been recorded.

# CHANGE MANAGEMENT PROCESS

A change is any proposed alteration to an approved requirement, acceptance criterion, device quantity, architecture, VLAN or IP plan, supplier, schedule, budget, security control, DSP method or project deliverable.

The approved requirements baseline is version 1.0. Approved changes will increment the version number. Verbal approval is not sufficient.

## Change workflow

- Submit a Project Change Request Form.

- Assign the request a change identification number.

- Record the requested change, reason, requester and affected requirements.

- Assess impacts on scope, cost, schedule, technical design, security, privacy, accessibility, risks, procurement, testing and training.

- Obtain a technical review and recommendation.

- Approve, reject or defer the request.

- If approved, update affected requirements, designs, schedules, budgets, risks and test plans.

- Implement the change in a controlled window.

- Retain backups and rollback arrangements.

- Complete the required verification and retesting.

- Notify affected stakeholders.

- Close the request after acceptance.

## Required change record

Each change record must contain:

- Change ID and date

- Requester

- Affected requirement IDs

- Current baseline version

- Description and reason

- Urgency

- Alternatives considered

- Cost and schedule impacts

- Technical and security impacts

- Risks and training impacts

- Decision and approver

- Implementation owner

- Target date

- Backup and rollback plan

- Test results

- Stakeholder communication

- Closure date

## Approval levels

| Level | Examples | Approval |
| --- | --- | --- |
| Major | Budget, final date, architecture, security boundary or major scope change | Project sponsor after project manager and technical review |
| Moderate | Equipment substitution, VLAN/IP modification or implementation-sequence change | Project Manager and technical owner; sponsor informed |
| Minor | Wording, document reference or low-risk configuration correction | Document or technical owner with Project Manager recording |
| Emergency | Immediate action required to contain a security incident or restore a critical service | Authorised operational lead followed by retrospective review |

# CONCLUSION

This plan establishes a controlled and traceable method for managing the Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade requirements.

It converts the selected Network 3 solution into identifiable business, functional, technical, performance, security, DSP, transition, accessibility and acceptance requirements.

The requirements register and traceability matrix connect stakeholder needs to design, implementation and evidence. The validation and verification process distinguishes between simulated, calculated, representative and production evidence.

The change-management process protects the 24-week schedule and AUD 184,800 baseline from unapproved variations.

The plan should be reviewed:

- At the end of requirements analysis

- Before procurement

- Before implementation

- Before user acceptance testing

- At project closure

Final acceptance will occur when all mandatory requirements have acceptable evidence, unresolved defects have an authorised decision, the documentation has been handed over and the project sponsor has signed the approval record.