RISK MANAGEMENT PLAN

Darvycom Australia Pty Ltd

| ID | 012025RMP |
| --- | --- |
| OWNER | DARVYCOM AUSTRALIA PTY LTD |
| PROJECT NAME | DARVYCOM BRISBANE ENGINEERING LABORATORY NETWORK AND DSP UPGRADE |
| ISSUE DATE | 10/12/2025 |
| LAST DATE SAVED | 23/08/2026 |
| VERSION | 1.0 |
| APPROVAL OF SPONSOR | Name: ____________________ Signature: ____________________ Date: __________ |

# DOCUMENT INFORMATION

Table of Contents

DOCUMENT INFORMATION	1

INTRODUCTION	3

RISK ASSESSMENT APPROACH	4

BENEFITS OF RISK MANAGEMENT/ASSESSMENT	5

RISK MANAGEMENT METHODOLOGY	6

RISK MATRIX	7

RISK REPORTING TEMPLATE	8

RISK RESPONSE BREAKDOWN	9

RISK RESPONSE TABLE	10

RISK FUNDING	11

CONCLUSION	12

# INTRODUCTION

This Risk Management Plan defines how risks will be identified, analysed, treated, monitored and reported for the Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade. It applies to the full 24-week project lifecycle, from requirements and procurement through implementation, testing, user acceptance, handover and closure.

The plan protects the approved scope, schedule, AUD $184,800 baseline budget, solution quality, information security, work health and safety, and continuity of laboratory operations. It covers Network 3 infrastructure and services across Laboratory Blocks A and B, including switching, routing, VLANs, VoIP, wireless, video conferencing, firewall and VPN connectivity, PRTG monitoring, servers, storage and DSP activities.

Risk management is a shared responsibility. Every team member, supplier and authorised stakeholder must promptly report a new risk, change in exposure, failed control or emerging issue to the Project Manager.

# RISK ASSESSMENT APPROACH

Risk assessment will be performed continuously and formally reviewed at requirements approval, design completion, procurement checkpoints, pre-cutover readiness, testing and UAT, handover and closure. Risks may be raised by the client, project team, technical specialists, suppliers or support personnel.

Each risk record will contain:

• A unique ID, category, date raised and concise cause-event-consequence description.

• The affected objective, deliverable, service, cost or milestone.

• A named risk owner and accountable response action owner.

• Existing controls, likelihood, impact and inherent risk score.

• Response strategy, actions, trigger, contingency, due date and status.

• Residual likelihood, impact and rating after treatment.

Risks will be classified as technical, cyber security/privacy, procurement/schedule, cost, operational, service quality/DSP, WHS, or people/change risks. Likelihood and impact are scored from 1 to 5 and multiplied to determine the rating. High and Extreme risks are escalated promptly; Medium risks require planned treatment and review; Low risks are monitored within normal project controls.

The Project Manager will review the register weekly and report material changes at project meetings and phase gates. A formal change request is required when a response may alter an approved baseline, deliverable or acceptance criterion.

# BENEFITS OF RISK MANAGEMENT/ASSESSMENT

Applying a structured risk process enables Darvycom to identify threats before they affect implementation or operations. The principal benefits are:

• Earlier detection of design, compatibility, security, capacity and procurement problems.

• Protection of the 24-week schedule and AUD $184,800 approved budget.

• Reduced likelihood of network outage, data/configuration loss and service disruption during cutover.

• Improved voice, video, wireless and DSP performance through planned testing, QoS and monitoring.

• Clear ownership, escalation pathways and evidence-based decisions.

• Safer rack, cabling, electrical and equipment-installation activities.

• Greater stakeholder confidence through documented controls, residual-risk acceptance and an auditable register.

• More reliable UAT, operational handover and future support of Network 3.

# RISK MANAGEMENT METHODOLOGY

Darvycom will use the following repeatable methodology throughout the project:

1. Establish context: Confirm the objectives, baselines, assumptions, constraints, stakeholders and risk criteria.

2. Identify: Use workshops, technical reviews, site inspections, lessons learned, supplier advice, test results and PRTG observations to identify risk events.

3. Analyse: Assess likelihood and impact before treatment and document the causes, consequences and existing controls.

4. Evaluate: Compare the score with the risk matrix and prioritise the response.

5. Treat: Select avoid, reduce, transfer/share, accept or escalate; assign actions, due dates, triggers and contingency measures.

6. Implement: Complete approved actions and retain evidence such as peer reviews, backups, test results, supplier confirmations and training records.

7. Monitor and report: Review controls and exposure weekly, report exceptions, and revise the register when circumstances change.

8. Close or hand over: Close a risk only when treatment is complete and exposure is acceptable. Transfer continuing operational risks during handover.

Roles and responsibilities

| Role | Risk-management responsibility |
| --- | --- |
| Project Sponsor / Client Representative | Approve risk tolerance, major treatment expenditure, baseline changes and acceptance of significant residual risks. |
| Project Manager – Leonardo Matias Ciarcia | Own this plan and the register; facilitate reviews; assign owners; escalate material exposure; report status; authorise actions within delegated authority. |
| Risk owner / technical lead | Analyse the assigned risk, implement controls, monitor triggers, retain evidence and report changes. |
| Project team and suppliers | Identify new risks, follow controls, communicate delays or failures and support treatment actions. |
| Darvycom users and support personnel | Participate in requirements review, training, UAT and operational risk handover. |

# RISK MATRIX

Risk score = Likelihood × Impact. The score represents inherent exposure before additional treatment and residual exposure after the planned controls are implemented.

| Score | Likelihood | Impact |
| --- | --- | --- |
| 1 | Rare – only in exceptional circumstances | Insignificant – negligible effect; handled through routine work |
| 2 | Unlikely – could occur but is not expected | Minor – limited rework, short delay or small local service effect |
| 3 | Possible – may occur during the project | Moderate – measurable cost/schedule effect or service degradation |
| 4 | Likely – expected in some circumstances | Major – milestone threat, material cost, outage or security impact |
| 5 | Almost certain – expected to occur | Severe – critical failure, serious injury, major breach or project objective not achieved |

Risk rating matrix

| Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 5 – Almost certain | 5 M | 10 H | 15 H | 20 E | 25 E |
| 4 – Likely | 4 L | 8 M | 12 H | 16 H | 20 E |
| 3 – Possible | 3 L | 6 M | 9 M | 12 H | 15 H |
| 2 – Unlikely | 2 L | 4 L | 6 M | 8 M | 10 H |
| 1 – Rare | 1 L | 2 L | 3 L | 4 L | 5 M |

Rating and escalation rules

| Rating | Score | Required action |
| --- | --- | --- |
| Low | 1–4 | Monitor through routine controls; review when conditions change. |
| Medium | 5–9 | Assign treatment and review at the weekly project meeting. |
| High | 10–16 | Prompt PM escalation, documented treatment, owner and target date; sponsor visibility. |
| Extreme | 17–25 | Immediate escalation. Pause affected work where safety, security or critical service exposure is unacceptable. |

# RISK REPORTING TEMPLATE

The following template will be used when a new risk is raised or an existing risk changes materially. The completed record is entered in the project risk register and reviewed by the Project Manager.

| Field | Required information |
| --- | --- |
| Risk ID and title | Unique reference and concise risk-event title |
| Date raised / raised by | Date identified and name or role of the person reporting it |
| Category | Technical, security/privacy, procurement/schedule, cost, operational, DSP/quality, WHS, or people/change |
| Risk description | Cause, uncertain event and potential consequence |
| Affected objective/deliverable | Service, milestone, cost, quality, security or acceptance requirement at risk |
| Risk owner | Person accountable for monitoring and coordinating the response |
| Existing controls | Controls already in place when the risk is assessed |
| Inherent assessment | Likelihood (1–5), impact (1–5), score and rating |
| Response and actions | Avoid, reduce, transfer/share, accept or escalate; list actions and action owners |
| Trigger / early warning | Observable condition that requires intervention |
| Contingency plan | Actions to reduce consequences if the event occurs |
| Target date | Date by which treatment is required |
| Residual assessment | Expected likelihood, impact, score and rating after treatment |
| Status and review date | Open, monitoring, escalated, occurred/issue, closed; next review date |
| Escalation / change decision | Sponsor decision or change-request reference when a baseline may be affected |

# RISK RESPONSE BREAKDOWN

The selected response must be proportionate to the exposure, feasible within project constraints and supported by a named owner, due date and evidence of completion.

Avoid: Remove the cause or change the approach so the threat no longer applies. Examples include replacing an incompatible component or rescheduling unsafe work.

Reduce: Lower likelihood and/or impact through preventive and detective controls such as peer review, staged testing, VLAN/QoS design, PRTG thresholds, backups and training.

Transfer or share: Allocate part of the exposure to a supplier or third party through warranty, support, contract conditions, insurance or specialist services. Darvycom retains responsibility for monitoring the outcome.

Accept: Retain a risk that is within tolerance when further treatment is not cost-effective. Define a trigger, contingency and review date; acceptance does not mean ignoring the risk.

Escalate: Refer the risk to the Project Sponsor when it exceeds the Project Manager’s authority, threatens a baseline or acceptance criterion, or creates unacceptable WHS, security or critical-service exposure.

If a risk event occurs, it will be managed as an issue while the related risk record remains linked for traceability. The Project Manager will initiate the contingency plan, assess cost and schedule effects, communicate with affected stakeholders and raise a change request when required. Significant residual risks must be accepted by the Project Sponsor / Client Representative before closure or operational handover.

# RISK RESPONSE TABLE

The following register records the principal risks identified for Network 3. Ratings shown as L/I use the 1–5 scales above. Status is Open unless a later review records otherwise.

| ID | Risk event | Inherent | Preventive treatment | Trigger and contingency | Owner / residual |
| --- | --- | --- | --- | --- | --- |
| R1 | Requirements or scope change causes rework, delay or unapproved cost. | 3/4 High 12 | Confirm requirements and acceptance criteria; maintain traceability; apply formal change control. | Trigger: new or changed requirement after approval. Assess impact, obtain sponsor decision and rebaseline only after approval. | Project Manager 2/3 Medium 6 |
| R2 | Equipment, licence or supplier delivery delay affects build and cutover dates. | 4/4 High 16 | Finalise BOM and quotes early; verify lead times; identify approved alternatives; track orders weekly. | Trigger: delivery threatens Weeks 14–15 installation. Use alternate supplier/component or resequence preparation and testing. | Procurement Lead 2/4 Medium 8 |
| R3 | Ports, PoE, cabling or UPS capacity is insufficient for the final device load. | 3/4 High 12 | Complete site, port, PoE and electrical load survey; retain spare capacity; validate UPS runtime. | Trigger: design review or capacity test fails. Add approved modules, cabling or UPS capacity using change and contingency controls. | Network Engineer 2/3 Medium 6 |
| R4 | Configuration error causes loss of connectivity or outage during implementation. | 3/5 High 15 | Peer-review configs; stage changes; back up known-good versions; use approved windows and rollback plans. | Trigger: critical connectivity or service loss. Isolate the change, roll back and restore the approved configuration before retesting. | Network Engineer 2/3 Medium 6 |
| R5 | Congestion or poor QoS reduces VoIP/video quality and DSP-related service performance. | 4/4 High 16 | Use VLAN segmentation, QoS, capacity checks, load testing and PRTG utilisation/latency thresholds. | Trigger: high utilisation, jitter, packet loss or failed quality test. Tune QoS, limit non-critical transfers and add capacity if approved. | Network Engineer 2/4 Medium 8 |
| R6 | Firewall or VPN weakness permits unauthorised access or exposes Darvycom information. | 3/5 High 15 | Apply least privilege, ACL review, strong authentication, secure management, patching, logging and security testing. | Trigger: failed security test or suspicious access. Isolate affected service, block traffic, revoke credentials and invoke incident procedure. | Security / Network Engineer 1/5 Medium 5 |
| R7 | Cisco CME, IP phone, firmware or DHCP compatibility prevents registration or calling. | 3/4 High 12 | Confirm supported models/firmware, voice VLAN and DHCP option; stage registration and call tests. | Trigger: phone fails to register or call. Restore known-good voice configuration, correct firmware/settings or use approved compatible equipment. | Voice Engineer 1/4 Low 4 |
| R8 | DSP design or tuning does not achieve required signal quality, SNR or stability. | 3/4 High 12 | Record baseline; perform spectrum, convolution and filter analysis; model and tune in stages; retain test evidence. | Trigger: result below agreed quality target or unstable. Revert parameters, analyse cause and test an alternative filter/configuration. | DSP Engineer 2/3 Medium 6 |
| R9 | Cutover disrupts laboratory data, voice, wireless or video services. | 3/4 High 12 | Pilot Block A; use staged block-by-block cutover, stakeholder notice, readiness checklist and backout plan. | Trigger: critical service loss or acceptance failure. Roll back affected stage, restore service and reschedule after corrective review. | PM / Network Engineer 2/3 Medium 6 |
| R10 | Users are not ready for IP phones, wireless, video conferencing or support procedures. | 3/3 Medium 9 | Provide role-based guides, training, UAT, demonstrations and early support arrangements. | Trigger: failed UAT or repeated use errors. Deliver additional training, quick guides and focused floor support. | Training Coordinator 1/3 Low 3 |
| R11 | Combined delays, rework or cost increases exceed schedule or budget tolerance. | 3/5 High 15 | Track milestones, actuals, commitments and forecast; control scope; review reserve and variances regularly. | Trigger: critical-path delay above five working days or forecast above baseline. Correct/resequence work and seek sponsor change decision before extra spend. | Project Manager 2/4 Medium 8 |
| R12 | Data, configurations or server services are lost or corrupted. | 3/5 High 15 | Use version control, regular configuration/data backups, NAS/UPS protection and tested restoration procedures. | Trigger: missing/corrupt record or server outage. Restore verified backup, rebuild/fail over service and investigate root cause. | Systems Administrator 1/5 Medium 5 |
| R13 | Rack, cabling, lifting or electrical work causes injury or equipment damage. | 2/5 High 10 | Site induction; qualified personnel; isolation and safe lifting; cable management; PPE; no unauthorised live work. | Trigger: unsafe condition, near miss or injury. Stop work, isolate the area, provide first aid, report and investigate before resuming. | PM / Site Supervisor 1/5 Medium 5 |

# RISK FUNDING

The approved AUD $184,800 project baseline includes an AUD $30,800 contingency reserve for approved in-scope risk responses. The reserve is not available for discretionary scope expansion or unapproved enhancements.

• Every proposed draw must reference the relevant risk ID, treatment action, estimated amount, justification and remaining exposure.

• The Project Manager validates the request and confirms budget availability; the Project Sponsor / Client Representative approves expenditure according to delegated authority and change-control requirements.

• Committed, actual and forecast response costs, together with the remaining reserve, will be reported during monthly budget and risk reviews.

• Supplier warranty, specialist support, replacement equipment, additional testing and approved capacity upgrades must be charged to the appropriate cost category and linked to the risk record.

• If the reserve is insufficient or a response changes the approved scope or baseline, additional funding must be authorised through formal change control before commitment or expenditure.

Unused contingency remains part of the approved project budget and will be reported at closure. Risk funding decisions and evidence will be retained with the budget records and change register.

# CONCLUSION

This Risk Management Plan provides a practical and auditable framework for controlling uncertainty throughout the Darvycom Brisbane Engineering Laboratory Network and DSP Upgrade. The approach supports safe implementation, secure and reliable Network 3 services, protection of the approved schedule and budget, and evidence-based acceptance of the completed solution.

The Project Manager will maintain the risk register until project closure. Risks will not be closed until actions are complete, evidence has been reviewed and residual exposure is within tolerance. Continuing operational risks will be documented and formally handed over to the Darvycom Project Sponsor / Client Representative with the final configurations, test records and support documentation.