SCOPE MANAGEMENT PLAN

DARVYCOM AUSTRALIA PTY LTD

| ID | 012025SM |
| --- | --- |
| OWNER | DARVYCOM AUSTRALIA PTY LTD |
| PROJECT NAME | DARVYCOM NETWORK UPGRADE AND APPLICATION DSP SYSTEMS |
| ISSUE DATE | 10/12/2025 |
| LAST DATE SAVED | 10/12/2025 |
| VERSION | 1.0 |
| APPROVAL OF SPONSOR |  |

Table of Contents

PROJECT OVERVIEW:	3

INTRODUCTION:	3

BACKGROUND:	4

PROJECT BREAKDOWN:	5

PROJECT SCOPE KEYPOINTS	5

SCOPE PLANNING:	6

WORK BREAKDOWN STRUCTURE:	7

SCOPE APPROVAL	8

SCOPE CHANGE CONTROL	8

CONCLUSION:	9

This template provides a guide for you to complete the scope management plan for the Darvycom Australia Pty Ltd project of cluster 6 of the ADIT TNE programme.  Please refer to the project scenario of Tasks 3 and 4 of Cluster 6 project for details regarding all aspects of this plan. Ensure you provide all relevant details for your report before submission.

# PROJECT OVERVIEW:

Darvycom Australia Pty Ltd is upgrading the network infrastructure and digital signal processing (DSP) capabilities of its Brisbane Engineering Laboratory, which is made up of two twin lab blocks. The current copper-based analogue PBX and limited data network are causing poor voice quality and do not support the growing number of users and services.

This project will design and implement a modern IP-based network and improved DSP solutions so the Brisbane lab can function as a regional office and support more clients, testing and research activities.

# INTRODUCTION:

The purpose of this Scope Management Plan is to describe how the scope of the Darvycom Brisbane Network & DSP Upgrade project will be defined, documented, approved and controlled.

This plan ensures that all work required to deliver the upgraded network and improved DSP capability is included, and that work not aligned with the agreed objectives is excluded. It also provides a reference for managing scope changes throughout the life of the project.

# BACKGROUND:

Darvycom currently operates an engineering laboratory in Brisbane with the following main infrastructure in each lab block:

- Eight analogue phone sets connected to a Panasonic hybrid PBX via copper wire.

- Eight computer systems.

- One data server.

- Basic networking switches, one internet router and one UPS system.

Staff have reported persistent voice quality issues and limited capacity for new services. The company plans to promote the Brisbane lab to a regional office and therefore needs:

- Twenty IP phones using VoIP.

- Twenty computers with updated operating systems and softphone applications.

- Forty headsets with microphones.

- A video conferencing system for client communication.

- Two data servers and one voice server with IP-PBX software.

- A VPN-capable router and four managed network switches.

The project also includes reviewing and improving DSP processes to increase signal-to-noise ratio (SNR) and overall communication quality.

# PROJECT BREAKDOWN:

At a high level, the project work is broken down into the following major areas:

- Project management and governance

      - Overall coordination, planning, monitoring and reporting.

- Requirements and analysis

      - Understanding business, network and DSP requirements and the limitations of the existing environment.

- Network design

      - Designing the upgraded IP network, including topology, addressing, VLANs, QoS, VPN and security.

- DSP design and simulation

      - Analysing current DSP behaviour and designing and simulating improved filters and algorithms.

- Procurement and preparation

      - Selecting, purchasing and preparing hardware and software required for the upgrade.

- Network implementation

      - Installing and configuring switches, router, servers, IP phones, headsets and video conferencing system.

- DSP implementation and testing

      - Implementing selected DSP configurations in the lab and testing their performance.

- Testing, training and handover

      - System testing, user acceptance testing, staff training and final handover.

These breakdown areas are expanded further in the Work Breakdown Structure section.

# PROJECT SCOPE KEYPOINTS

In Scope

- Design and implementation of an IP-based network across both Brisbane lab blocks, including:

      - 20 IP phones using VoIP.

      - 20 computers with updated operating systems and softphone applications.

      - 40 headsets with microphones.

      - 1 video conferencing system.

      - 2 data servers.

      - 1 voice server with suitable IP-PBX software.

      - 1 VPN-capable router.

      - 4 managed PoE network switches.

- Configuration of VLANs, QoS, VPN and basic security policies to support voice, data and management traffic.

- Review and analysis of existing DSP processes and design of improved DSP solutions to increase SNR.

- Simulation of DSP algorithms and comparison of derived vs simulated results.

- Implementation and testing of the selected DSP configuration in the lab environment.

- Development of documentation (designs, configurations, test results) and basic user training for lab staff.

Out of Scope

- Network or telephony changes at Darvycom sites outside the Brisbane Engineering Laboratory.

- Full production rollout beyond the two lab blocks.

- Long-term operational support and monitoring after project closure.

- Major changes to external carrier services or corporate WAN, other than VPN configuration necessary for this project.

# SCOPE PLANNING:

Scope planning for this project is based on:

- The requirements given in the Darvycom case study and discussions with the client (trainer/assessor).

- Site review of the existing lab infrastructure and current constraints.

- Identification of business needs (better voice quality, more users, regional office capability).

- Technical requirements for network performance and DSP improvements.

The detailed scope is captured in:

- The Scope Statement in this plan.

- The Work Breakdown Structure (WBS).

- Supporting documents such as network design diagrams and DSP design specifications.

The initial scope baseline will be established once this Scope Management Plan, the WBS and related design documents are approved by the client.

# WORK BREAKDOWN STRUCTURE:

Level 1 – Darvycom Brisbane Network & DSP Upgrade

- Project Management
1.1 Project initiation and charter
1.2 Develop Project Management Plan and sub-plans
1.3 Stakeholder and client meetings
1.4 Ongoing monitoring and reporting
1.5 Project closure and lessons learned

- Requirements and Analysis
2.1 Review existing telephony and data network
2.2 Gather business and user requirements
2.3 Analyse current voice quality and network performance
2.4 Analyse current DSP process and identify limitations

- Network Design
3.1 High-level network architecture for both lab blocks
3.2 Detailed LAN design (VLANs, IP addressing, QoS policies)
3.3 Router, VPN and firewall design
3.4 IP-PBX and video conferencing design

- DSP Design and Simulation
4.1 Define DSP performance and SNR requirements
4.2 Model existing DSP chain and LTI behaviour
4.3 Design candidate DSP filters and algorithms
4.4 Run simulations and compare with analytical results
4.5 Select preferred DSP configuration and document design

- Procurement and Preparation
5.1 Finalise list of hardware, software and licences
5.2 Obtain quotes and approvals
5.3 Order and receive equipment and licences
5.4 Prepare lab racks, power and cabling for installation

- Network Implementation
6.1 Install and configure managed PoE switches
6.2 Install and configure VPN-capable router
6.3 Install and configure data servers and voice server
6.4 Deploy IP phones and headsets
6.5 Install and configure video conferencing system
6.6 Configure VLANs, QoS, VPN and basic firewall rules

- DSP Implementation and Testing
7.1 Implement chosen DSP filters/configuration in lab environment
7.2 Integrate DSP elements with communication systems
7.3 Test SNR and DSP behaviour; refine parameters if needed

- Testing, Training and Handover
8.1 Perform network, VoIP and performance testing
8.2 Perform DSP tests and confirm SNR improvements
8.3 Conduct user acceptance testing with lab staff
8.4 Deliver training sessions and user guides
8.5 Handover documentation and obtain final sign-off

# SCOPE APPROVAL

Scope approval will occur when:

- This Scope Management Plan and the detailed Scope Statement and WBS are reviewed by the client (trainer/assessor acting as Darvycom representative).

- Any required clarifications or adjustments from the client are incorporated.

- The client confirms, in writing or by signature, that the defined scope and deliverables meet their expectations.

# SCOPE CHANGE CONTROL

Scope change control ensures that any modification to the project scope is properly assessed and approved.

The process is:

- Raise change request

      - Any stakeholder who wants to change the scope (e.g. add devices, change requirements, extend DSP work) completes a Change Request Form.

- Initial review

      - The Project Manager reviews the request for completeness and checks whether it is consistent with project objectives.

- Impact analysis

      - The Project Manager and relevant team members assess the impact on:

    - Schedule (additional time required)

    - Cost (additional funding or resources)

    - Quality and technical risk

    - Other project constraints

- Decision

      - The client / sponsor decides to approve, reject or defer the change request.

- Baseline update

      - If the change is approved, the scope baseline, schedule and budget (if affected) are updated.

      - The change is recorded in the change log and communicated to all relevant stakeholders.

- Implementation

      - The approved change is planned and implemented as part of the normal project work.

# CONCLUSION:

This Scope Management Plan defines what is included in the Darvycom Brisbane Network & DSP Upgrade project and how that scope will be controlled.

By clearly describing the background, project breakdown, key scope points, WBS and change control process, this plan provides a solid foundation for managing the project and avoiding uncontrolled scope creep. It will be used together with the other project sub-plans (schedule, cost, risk, quality, communication and procurement) to guide the successful delivery of the upgraded network and DSP capabilities for Darvycom’s Brisbane Engineering Laboratory.